## Sheet3
Ach Month | (Multiple Items)
Remark | QTY | Value
1.1. eWCC approved | 6 | 21433776
1.3. eWCC submit | 10 | 63866034
2.1. MS date NA | 1 | 6747589
2.2. NY create in eWCC | 50 | 420550372
2.10. Wrong Ewcc Status | 15 | 98406439
3.3. PO NY ready | 4 | 21963237
3.4. Need Revise PO | 5 | 8079700
4.7. Waiting Doc MSFI | 32 | 208126544
5.1 Waiting Doc TSSR | 10 | 24744640
8.3. NY MSFI App | 45 | 299917620
9.1. Cancel PO | 43 | 29895178
10. Implemented by Other Partner | 2 | 13495178
(blank) |  | 1208968590
Grand Total | 223 | 2426194897

## Sheet1
842 | 827 |  | 853 | 824 | 3672735005 | 422 | 836 | 90 | 412 | 3672735005 | 629
Site ID | Site Name | PO Status | PO Number | SOW | PO Amount | eWCC Submit | eWCC Approve | WCC number | Ach Month | PO Amount | Remark | Reason | MS Date
133614 | DMT Supersemar | PO Released | 34237284 | A.6. TI Service | 6747589 |  |  |  |  | 6747589 | 2.1. MS date NA
133777 | Protelindo Kalijaten_GF | PO Released | 34208830 | A.6. TI Service | 2269816 | 2017-07-20 | 2017-07-25 | 3417/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 2269816 | 1.1. eWCC approved |  | 2017-06-07
133797 | Protelindo_Petemon | PO Released | 34208797 | A.6. TI Service | 2269816 |  |  |  |  | 2269816 | 8.3. NY MSFI App |  | 2017-03-23
133815 | Protelindo_Simorukun | PO Released | 34203580 | A.6. TI Service | 2269816 | 2017-07-26 | 2017-07-28 | 4185/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 2269816 | 1.1. eWCC approved |  | 2017-03-23
133874 | Watu Mujur_GF | PO Released | 34235121 | A.6. TI Service | 6747589 | 2017-07-19 | 2017-07-25 | 3419/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-06-14
133887 | Protelindo_Soekarno Hatta | PO Released | 34235252 | A.6. TI Service | 6747589 | 2017-07-19 | 2017-07-28 | 4043/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-06-09
134073 | Ponpes Lirboyo | PO Released | 34236878 | A.6. TI Service | 6747589 | 2017-07-22 | 2017-07-25 | 3425/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-06-21
134075 | B2S_Protelindo Balowerti | PO Released | 34237784 | A.6. TI Service | 6747589 | 2017-07-22 | 2017-07-25 | 3426/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-06-21
134076 | B2S_Protelindo Ngadirejo | PO Released | 34235245 | A.6. TI Service | 6747589 | 2017-07-22 | 2017-07-25 | 3427/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-06-21
630473 | GIK_PETUNG PASURUAN | PO Released | 34203578 | A.6. TI Service | 2269816 |  |  |  |  | 2269816 | 8.3. NY MSFI App |  | 2017-03-24
630506 | XLPandaan | PO Released | 34275871 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
631012 | Ketindan lawang | PO Released | 34203549 | A.6. TI Service | 2269816 | 2017-07-21 | 2017-07-25 | 3470/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 2269816 | 1.1. eWCC approved |  | 2017-06-07
631014 | TAMAN SULFAT | PO Released | 34235287 | A.6. TI Service | 6747589 | 2017-07-21 | 2017-07-25 | 3471/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-05-30
631043 | RAMAYANA KEDIRI | PO Released | 34235322 | A.6. TI Service | 6747589 | 2017-07-22 | 2017-07-25 | 3473/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-26
631045 | ISATPARE | PO Released | 34237886 | A.6. TI Service | 6747589 | 2017-07-22 | 2017-07-25 | 3474/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-06-14
631053 | Gayam Mojoroto | PO Released | 34201036 | A.6. TI Service | 2269816 | 2017-07-22 | 2017-07-25 | 3477/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 2269816 | 1.1. eWCC approved |  | 2017-06-21
631054 | Ngampel | PO Released | 34203562 | A.6. TI Service | 2269816 | 2017-07-22 | 2017-07-25 | 3478/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 2269816 | 1.1. eWCC approved |  | 2017-06-14
631055 | UNIVKEDIRI | PO Released | 34203574 | A.6. TI Service | 2269816 | 2017-07-21 | 2017-07-25 | 3479/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 2269816 | 1.1. eWCC approved |  | 2017-06-14
631058 | SEKOTO | PO Released | 34203567 | A.6. TI Service | 2269816 | 2017-07-21 | 2017-07-25 | 3480/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 2269816 | 1.1. eWCC approved |  | 2017-06-21
134085 | B2S_Jodipan_Weatan | PO Released | 34235215 | A.6. TI Service | 6747589 | 2017-07-21 | 2017-07-25 | 3428/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-05-19
134266 | KNU_3G Panggungrejo Kepanjen | PO Released | 34237934 | A.6. TI Service | 6747589 | 2017-07-22 | 2017-07-25 | 3429/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-06-14
131672 | Thamrin - Kartoharjo E | PO Released | 34236753 | A.6. TI Service | 6747589 | 2017-07-12 | 2017-07-16 | 1660/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-01
130742 | XL - TAMBAK PINGGIR | PO Released | 34238417 | A.6. TI Service | 6747589 | 2017-07-26 | 2017-07-28 | 4328/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-10
131394 | Tropodo Niaga - Waru B | PO Released | 34238438 | A.6. TI Service | 6747589 | 2017-07-24 | 2017-07-26 | 3550/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-10
131486 | Wedoro - Waru B | PO Released | 34238381 | A.6. TI Service | 6747589 | 2017-07-24 | 2017-07-26 | 3553/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-10
131666 | TELCOINDO - KEPUH | PO Released | 34238340 | A.6. TI Service | 6747589 |  |  |  |  | 6747589 | 8.3. NY MSFI App |  | 2017-03-10
132935 | IBS_Kepuh Kiriman | PO Released | 34238402 | A.6. TI Service | 6747589 |  |  |  |  | 6747589 | 8.3. NY MSFI App |  | 2017-03-10
130137 | Semampir - Sedati | PO Released | 34238363 | A.6. TI Service | 6747589 | 2017-07-04 | 2017-07-12 | 1510/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-10
133136 | IBS_PABEAN | PO Released | 34238316 | A.6. TI Service | 6747589 | 2017-07-26 | 2017-07-28 | 4190/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-11
130164 | Mulyo Agung Dau | PO Released | 34235228 | A.6. TI Service | 6747589 | 2017-07-12 | 2017-07-19 | 1728/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-12
130275 | Klojen | PO Released | 34235272 | A.6. TI Service | 6747589 | 2017-07-04 | 2017-07-12 | 1514/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-12
130293 | LA.Sucipto - Blimbing | PO Released | 34235281 | A.6. TI Service | 6747589 | 2017-07-04 | 2017-07-12 | 1516/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-12
130474 | Raya Wendit Timur - Pakis | PO Released | 34235235 | A.6. TI Service | 6747589 | 2017-07-13 | 2017-07-19 | 1736/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-13
130279 | Brigjen Katamso - Klojen | PO Released | 34235205 | A.6. TI Service | 6747589 | 2017-07-04 | 2017-07-25 | 3313/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-13
130291 | Kerapu-Blimbing | PO Released | 34235175 | A.6. TI Service | 6747589 | 2017-07-08 | 2017-07-13 | 1561/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-13
130599 | Gondanglegi Wetan - Gondanglegi | PO Released | 34238170 | A.6. TI Service | 6747589 | 2017-07-12 | 2017-07-16 | 1651/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-14
130303 | Bandulan-Sukun | PO Released | 34235300 | A.6. TI Service | 6747589 | 2017-07-04 | 2017-07-12 | 1517/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-14
132665 | PAGEDANGAN_GF | PO Released | 34237769 | A.6. TI Service | 6747589 | 2017-07-04 | 2017-07-12 | 1528/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-14
132361 | Turen | PO Released | 34237750 | A.6. TI Service | 6747589 | 2017-07-18 | 2017-07-19 | 1767/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-14
131444 | Sidodadi - Kepanjen B | PO Released | 34238018 | A.6. TI Service | 6747589 | 2017-07-08 | 2017-07-14 | 1593/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-14
130710 | PROTELINDO - PAKISAJI | PO Released | 34237727 | A.6. TI Service | 6747589 | 2017-07-08 | 2017-07-13 | 1576/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-15
132664 | SIMPANG MATARAM_GF | PO Released | 34237490 | A.6. TI Service | 6747589 | 2017-07-12 | 2017-07-16 | 1680/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-15
130241 | Garuda - Pakis Aji | PO Released | 34238201 | A.6. TI Service | 6747589 | 2017-07-04 | 2017-07-12 | 1512/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-15
130276 | Mas FM | PO Released | 34235258 | A.6. TI Service | 6747589 | 2017-07-04 | 2017-07-12 | 1515/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-17
132697 | TBG_LAWANG | PO Released | 34237809 | A.6. TI Service | 6747589 | 2017-07-08 | 2017-07-14 | 1614/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-17
130690 | Madukoro - Lawang | PO Released | 34238081 | A.6. TI Service | 6747589 | 2017-07-11 | 2017-07-13 | 1575/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-17
130147 | Aloon-aloon Timur - Mangunharjo | PO Released | 34236918 | A.6. TI Service | 6747589 | 2017-07-18 | 2017-07-19 | 1727/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-18
131685 | Taman Praja - Taman B | PO Released | 34236989 | A.6. TI Service | 6747589 | 2017-07-12 | 2017-07-16 | 1662/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-19
132587 | Axis_Bujel | PO Released | 34237720 | A.6. TI Service | 6747589 | 2017-07-12 | 2017-07-16 | 1678/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-20
132364 | ISAT Lawang | PO Released | 34237679 | A.6. TI Service | 6747589 | 2017-07-08 | 2017-07-14 | 1605/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-22
132634 | ISAT_KEDIRI_CITY | PO Released | 34237835 | A.6. TI Service | 6747589 | 2017-07-12 | 2017-07-16 | 1679/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-23
132051 | Susuan Gampangrejo_GF | PO Released | 34237701 | A.6. TI Service | 6747589 | 2017-07-12 | 2017-07-16 | 1668/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-23
133153 | STP_Bedali Lawang | PO Released | 34237572 | A.6. TI Service | 6747589 | 2017-07-28 |  |  |  | 6747589 | 1.3. eWCC submit |  | 2017-03-23
130625 | Masjid - Gampengrejo | PO Released | 34237340 | A.6. TI Service | 6747589 | 2017-07-12 | 2017-07-19 | 1740/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-23
130484 | Hayam Wuruk - Kediri B | PO Released | 34235309 | A.6. TI Service | 6747589 | 2017-07-12 | 2017-07-16 | 1648/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-23
132848 | DMT_Tanjung Pagu | PO Released | 34237461 | A.6. TI Service | 6747589 | 2017-07-12 | 2017-07-16 | 1681/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-24
132551 | NTS_Lirboyo | PO Released | 34237355 | A.6. TI Service | 6747589 | 2017-07-12 | 2017-07-16 | 1675/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-24
132553 | Axis_Kali Ombo | PO Released | 34235180 | A.6. TI Service | 6747589 | 2017-07-12 | 2017-07-16 | 1676/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-24
131738 | ISAT Rembang Kediri | PO Released | 34237824 | A.6. TI Service | 6747589 | 2017-07-18 | 2017-07-19 | 1756/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-24
131845 | ISAT Ngronggo | PO Released | 34237795 | A.6. TI Service | 6747589 | 2017-07-12 | 2017-07-16 | 1665/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-24
132373 | ISAT PATIHAN | PO Released | 34236947 | A.6. TI Service | 6747589 | 2017-07-12 | 2017-07-16 | 1673/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-26
132364 | ISAT Lawang | PO Released | 34531357 | 1.9.1 TI Material Delivery | 400000 | 2017-06-15 | 2017-06-22 | 1216/eWCC/H3I/INH/C2/VI/2017 | 2017-06-01 | 400000 | 1.1. eWCC approved |  | 2017-05-18
134085 | B2S_Jodipan_Weatan | PO Released | 34530991 | 1.9.1 TI Material Delivery | 400000 | 2017-06-15 | 2017-06-16 | 1174/eWCC/H3I/INH/C2/VI/2017 | 2017-06-01 | 400000 | 1.1. eWCC approved |  | 2017-05-19
630225 | B2S Protelindo Oro-Oro Ombo | PO Released | 34531237 | 1.9.1 TI Material Delivery | 400000 | 2017-06-13 | 2017-06-22 | 1117/eWCC/H3I/INH/C2/VI/2017 | 2017-06-01 | 400000 | 1.1. eWCC approved |  | 2017-05-19
130307 | Bakalankrajan | PO Released | 34531035 | 1.9.1 TI Material Delivery | 400000 | 2017-06-13 | 2017-06-16 | 1116/eWCC/H3I/INH/C2/VI/2017 | 2017-06-01 | 400000 | 1.1. eWCC approved |  | 2017-05-19
130303 | Bandulan-Sukun | PO Released | 34531015 | 1.9.1 TI Material Delivery | 400000 | 2017-06-13 | 2017-06-16 | 1115/eWCC/H3I/INH/C2/VI/2017 | 2017-06-01 | 400000 | 1.1. eWCC approved |  | 2017-05-19
62562 | Gedung Nasional - Tamansari | PO Released | 34727243 | A.6. TI Service SouthSum | 2199454 | 2017-07-22 | 2017-07-25 | 3177/eWCC/H3I/INH/E6/VII/2017 | 2017-07-01 | 2199454 | 1.1. eWCC approved |  | 2017-03-22
62609 | Raya Muntok PKP | PO Released | 34727229 | A.6. TI Service SouthSum | 2199454 | 2017-07-27 | 2017-07-28 | 4125/eWCC/H3I/INH/E6/VII/2017 | 2017-07-01 | 2199454 | 1.1. eWCC approved |  | 2017-03-27
62618 | Tegal PKP | PO Released | 34727226 | A.6. TI Service SouthSum | 2199454 | 2017-07-31 | 2017-08-01 | 4914/eWCC/H3I/INH/E6/VIII/2017 | 2017-08-01 | 2199454 | 1.1. eWCC approved |  | 2017-03-23
62615 | Al Yusro PKP | PO Released | 34727186 | A.6. TI Service SouthSum | 2199454 | 2017-07-31 | 2017-08-01 | 4913/eWCC/H3I/INH/E6/VIII/2017 | 2017-08-01 | 2199454 | 1.1. eWCC approved |  | 2017-03-27
62526 | Pasar Prabumulih | PO Released | 34725796 | A.6. TI Service SouthSum | 6281690 |  |  |  |  | 6281690 | 8.3. NY MSFI App |  | 2017-03-25
60436 | Taman Murni - Gunung Ibul Bara | PO Released | 34725792 | A.6. TI Service SouthSum | 6281690 |  |  |  |  | 6281690 | 8.3. NY MSFI App |  | 2017-03-23
60126 | Arimbi - Prabu Jaya | PO Released | 34725788 | A.6. TI Service SouthSum | 6281690 |  |  |  |  | 6281690 | 4.7. Waiting Doc MSFI |  | 2017-03-27
62527 | Prabujaya II | PO Released | 34725781 | A.6. TI Service SouthSum | 6281690 |  |  |  |  | 6281690 | 4.7. Waiting Doc MSFI |  | 2017-03-21
60124 | Perwira - Pasar I | PO Released | 34725772 | A.6. TI Service SouthSum | 6281690 |  |  |  |  | 6281690 | 8.3. NY MSFI App |  | 2017-03-11
62194 | Muara Enim | PO Released | 34725758 | A.6. TI Service SouthSum | 6281690 |  |  |  |  | 6281690 | 8.3. NY MSFI App |  | 2017-03-15
60125 | Mayor Rudy Lingga I - Tanjung Enim | PO Released | 34725743 | A.6. TI Service SouthSum | 6281690 |  |  |  |  | 6281690 | 4.7. Waiting Doc MSFI |  | 2017-03-22
62764 | Batu raja 4 | PO Released | 34725724 | A.6. TI Service SouthSum | 6281690 | 2017-07-27 | 2017-07-28 | 4127/eWCC/H3I/INH/E3/VII/2017 | 2017-07-01 | 6281690 | 1.1. eWCC approved |  | 2017-04-16
62524 | Prabu Jaya | PO Released | 34725711 | A.6. TI Service SouthSum | 6281690 | 2017-07-22 | 2017-07-25 | 3176/eWCC/H3I/INH/E3/VII/2017 | 2017-07-01 | 6281690 | 1.1. eWCC approved |  | 2017-03-13
62135 | TRIFIKA IDL | PO Released | 34725691 | A.6. TI Service SouthSum | 6281690 | 2017-07-27 | 2017-07-28 | 4122/eWCC/H3I/INH/E3/VII/2017 | 2017-07-01 | 6281690 | 1.1. eWCC approved |  | 2017-03-26
62048 | Kedaton | PO Released | 34725675 | A.6. TI Service SouthSum | 6281690 | 2017-07-27 | 2017-07-28 | 4120/eWCC/H3I/INH/E3/VII/2017 | 2017-07-01 | 6281690 | 1.1. eWCC approved |  | 2017-03-26
62525 | Tugu Kecil | PO Released | 34725658 | A.6. TI Service SouthSum | 6281690 |  |  |  |  | 6281690 | 4.7. Waiting Doc MSFI |  | 2017-03-22
62523 | Gunung Ibul Barat | PO Released | 34725645 | A.6. TI Service SouthSum | 6281690 |  |  |  |  | 6281690 | 4.7. Waiting Doc MSFI |  | 2017-03-20
62069 | Kayu Agung | PO Released | 34725626 | A.6. TI Service SouthSum | 6281690 |  |  |  |  | 6281690 | 4.7. Waiting Doc MSFI |  | 2017-03-27
61746 | Keban Agung | PO Released | 34725614 | A.6. TI Service SouthSum | 6281690 |  |  |  |  | 6281690 | 4.7. Waiting Doc MSFI |  | 2017-03-21
60486 | Simpang_Kompi | PO Released | 34725596 | A.6. TI Service SouthSum | 6281690 |  |  |  |  | 6281690 | 4.7. Waiting Doc MSFI |  | 2017-04-08
61529 | Kutilang - Karang raja | PO Released | 34725583 | A.6. TI Service SouthSum | 6281690 |  |  |  |  | 6281690 | 4.7. Waiting Doc MSFI |  | 2017-03-23
61586 | UNSRI Indralaya | PO Released | 34725568 | A.6. TI Service SouthSum | 6281690 | 2017-07-27 | 2017-07-28 | 4146/eWCC/H3I/INH/E3/VII/2017 | 2017-07-01 | 6281690 | 1.1. eWCC approved |  | 2017-03-17
62539 | Gunung Ibul Barat - Prabumulih Timur | PO Released | 34725554 | A.6. TI Service SouthSum | 6281690 |  |  |  |  | 6281690 | 8.3. NY MSFI App |  | 2017-03-20
60641 | Protelindo / Kol.Dani Effendi - Wonosari | PO Released | 34725538 | A.6. TI Service SouthSum | 6281690 |  |  |  |  | 6281690 | 8.3. NY MSFI App |  | 2017-03-24
62049 | PRABU JAYA / PRABUMULIH TIMUR | PO Released | 34725518 | A.6. TI Service SouthSum | 6281690 | 2017-07-27 | 2017-07-28 | 4121/eWCC/H3I/INH/E3/VII/2017 | 2017-07-01 | 6281690 | 1.1. eWCC approved |  | 2017-03-23
60503 | Kompleks PT. Bukit Asam Tanjung Enim Sumsel | PO Released | 34725506 | A.6. TI Service SouthSum | 6281690 |  |  |  |  | 6281690 | 4.7. Waiting Doc MSFI |  | 2017-03-22
61634 | Prabumulih - Prabumulih Barat | PO Released | 34725486 | A.6. TI Service SouthSum | 6281690 |  |  |  |  | 6281690 | 4.7. Waiting Doc MSFI |  | 2017-03-18
62164 | Inra laya Indah | PO Released | 34725463 | A.6. TI Service SouthSum | 6281690 | 2017-07-27 | 2017-07-28 | 4123/eWCC/H3I/INH/E3/VII/2017 | 2017-07-01 | 6281690 | 1.1. eWCC approved |  | 2017-03-20
61506 | Jaman - Tegal Rejo | PO Released | 34725440 | A.6. TI Service SouthSum | 6281690 | 2017-07-29 | 2017-07-31 | 4651/eWCC/H3I/INH/E3/VII/2017 | 2017-07-01 | 6281690 | 1.1. eWCC approved |  | 2017-03-13
61528 | Gunung Kemala - Patih Galung | PO Released | 34725424 | A.6. TI Service SouthSum | 6281690 | 2017-07-27 | 2017-07-28 | 4145/eWCC/H3I/INH/E3/VII/2017 | 2017-07-01 | 6281690 | 1.1. eWCC approved |  | 2017-03-14
62230 | Mitratel_Prabumulih | PO Released | 34725410 | A.6. TI Service SouthSum | 6281690 |  |  |  |  | 6281690 | 8.3. NY MSFI App |  | 2017-03-27
62083 | Cambai | PO Released | 34725400 | A.6. TI Service SouthSum | 6281690 |  |  |  |  | 6281690 | 8.3. NY MSFI App |  | 2017-03-22
62197 | DMT_Tanjung Enim | PO Released | 34725394 | A.6. TI Service SouthSum | 6281690 |  |  |  |  | 6281690 | 8.3. NY MSFI App |  | 2017-03-14
61034 | Bambang Utoyo - Pasar III | PO Released | 34725387 | A.6. TI Service SouthSum | 6281690 |  |  |  |  | 6281690 | 8.3. NY MSFI App |  | 2017-03-15
61591 | TANJUNG_ENIM | PO Released | 34725380 | A.6. TI Service SouthSum | 6281690 |  |  |  |  | 6281690 | 8.3. NY MSFI App |  | 2017-03-13
61721 | Padat Karya - Gunung Ibul | PO Released | 34725350 | A.6. TI Service SouthSum | 6281690 | 2017-07-27 | 2017-07-28 | 4119/eWCC/H3I/INH/E3/VII/2017 | 2017-07-01 | 6281690 | 1.1. eWCC approved |  | 2017-03-21
62574 | Timbangan | PO Released | 34725282 | A.6. TI Service SouthSum | 6281690 | 2017-07-27 | 2017-07-28 | 4124/eWCC/H3I/INH/E3/VII/2017 | 2017-07-01 | 6281690 | 1.1. eWCC approved |  | 2017-03-21
62762 | Bukit Asam - Tg Enim | PO Released | 34724974 | A.6. TI Service SouthSum | 1769845 | 2017-07-31 | 2017-08-01 | 4916/eWCC/H3I/INH/E3/VIII/2017 | 2017-08-01 | 1769845 | 1.1. eWCC approved |  | 2017-03-10
62760 | TANJUNG ENIM LAWANG KIDUL | PO Released | 34724920 | A.6. TI Service SouthSum | 1769845 | 2017-07-31 | 2017-08-01 | 4915/eWCC/H3I/INH/E3/VIII/2017 | 2017-08-01 | 1769845 | 1.1. eWCC approved |  | 2017-03-24
62745 | Puyuh Raya PKP | PO Released | 34724856 | A.6. TI Service SouthSum | 1769845 | 2017-07-31 | 2017-07-31 | 4908/eWCC/H3I/INH/E6/VII/2017 | 2017-07-01 | 1769845 | 1.1. eWCC approved |  | 2017-03-20
62759 | Majasari - Prabumulih | PO Released | 34724770 | A.6. TI Service SouthSum | 1769845 |  |  |  |  | 1769845 | 4.7. Waiting Doc MSFI |  | 2017-03-24
62681 | R Hundani Gabek II | PO Released | 34724699 | A.6. TI Service SouthSum | 1769845 | 2017-07-27 | 2017-07-28 | 4126/eWCC/H3I/INH/E6/VII/2017 | 2017-07-01 | 1769845 | 1.1. eWCC approved |  | 2017-03-14
62701 | Gunung Ibul Prabumulih | PO Released | 34724612 | A.6. TI Service SouthSum | 1769845 |  |  |  |  | 1769845 | 4.7. Waiting Doc MSFI |  | 2017-03-24
62761 | SUBDENPOM PRABUMULIH | PO Released | 34724558 | A.6. TI Service SouthSum | 1769845 |  |  |  |  | 1769845 | 8.3. NY MSFI App |  | 2017-03-24
62661 | H. Rakhyan | PO Released | 34724495 | A.6. TI Service SouthSum | 1769845 |  |  |  |  | 1769845 | 4.7. Waiting Doc MSFI |  | 2017-03-11
62652 | Toko Bintang Baru | PO Released | 34723956 | A.6. TI Service SouthSum | 2199454 | 2017-07-31 | 2017-07-31 | 4907/eWCC/H3I/INH/E3/VII/2017 | 2017-07-01 | 2199454 | 1.1. eWCC approved |  | 2017-02-19
62553 | Prabumulih Baru | PO Released | 34723927 | A.6. TI Service SouthSum | 2199454 |  |  |  |  | 2199454 | 4.7. Waiting Doc MSFI |  | 2017-03-24
212786 | Baddoka | PO Released | 34715531 | Add Cost MKS | 1707634 |  |  |  |  | 1707634
213148 | Pettuadae-Turikale | PO Released | 34715479 | Add Cost MKS | 880225 |  |  |  |  | 880225
212781 | Mambue | PO Released | 34715461 | Add Cost MKS | 1468685 |  |  |  |  | 1468685
212266 | Bulukunyi-Polsel-Takalar | PO Released | 34715442 | Add Cost MKS | 1654818 |  |  |  |  | 1654818
212122 | Pattalassang | PO Released | 34715422 | Add Cost MKS | 1654818 |  |  |  |  | 1654818
212131 | Tanralili | PO Released | 34715312 | Add Cost MKS | 2482227 |  |  |  |  | 2482227
212903 | Attang Ale | PO Released | 34714950 | Add Cost MKS | 827409 |  |  |  |  | 827409
212706 | Bonto-Bonto | PO Released | 34714947 | Add Cost MKS | 827409 |  |  |  |  | 827409
212647 | Tekolabbua | PO Released | 34714945 | Add Cost MKS | 827409 |  |  |  |  | 827409
212153 | Bungoro Pangkep | PO Released | 34714942 | Add Cost MKS | 827409 |  |  |  |  | 827409
212137 | Tonasa | PO Released | 34714940 | Add Cost MKS | 827409 |  |  |  |  | 827409
212254 | Taman roya | PO Released | 34714938 | Add Cost MKS | 827409 |  |  |  |  | 827409
212055 | Limbung | PO Released | 34714935 | Add Cost MKS | 827409 |  |  |  |  | 827409
212054 | Mangara Bombang | PO Released | 34714932 | Add Cost MKS | 827409 |  |  |  |  | 827409
212358 | Bili Bili | PO Released | 34714930 | Add Cost MKS | 827409 |  |  |  |  | 827409
212271 | Padi Valley | PO Released | 34714926 | Add Cost MKS | 827409 |  |  |  |  | 827409
212231 | MALINO, SULAWESI | PO Released | 34714924 | Add Cost MKS | 827409 |  |  |  |  | 827409
212146 | Benteng Gajah | PO Released | 34714922 | Add Cost MKS | 827409 |  |  |  |  | 827409
212135 | Lekopancing | PO Released | 34714920 | Add Cost MKS | 827409 |  |  |  |  | 827409
212002 | Bonto Lebang - Galesong Utara | PO Released | 34714895 | Add Cost MKS | 827409 |  |  |  |  | 827409
|  | PO Released | 34714867 |  | 5122902 |  |  |  |  | 5122902
213116 | 3G_Daya Kima | PO Released | 34714834 | Add Cost MKS | 1707634 |  |  |  |  | 1707634
212119 | Kanaungan | PO Released | 34714811 | Add Cost MKS | 880225 |  |  |  |  | 880225
212089 | Malewang | PO Released | 34714809 | Add Cost MKS | 1760450 |  |  |  |  | 1760450
213143 | TBG Citra | PO Released | 34714807 | Add Cost MKS | 880225 |  |  |  |  | 880225
213097 | Sanrangan | PO Released | 34714806 | Add Cost MKS | 880225 |  |  |  |  | 880225
212929 | Allepolea - Lau | PO Released | 34714778 | Add Cost MKS | 880225 |  |  |  |  | 880225
213133 | Taman Sudiang | PO Released | 34714369 | Add Cost MKS | 880225 |  |  |  |  | 880225
212110 | Moncong Maros | PO Released | 34714355 | Add Cost MKS | 880225 |  |  |  |  | 880225
212109 | KIMA 8 | PO Released | 34714287 | Add Cost MKS | 880225 |  |  |  |  | 880225
130030 | 0 | PO Released | 34689047 | A.6. TI Service | 6747589 |  |  |  |  | 6747589 | 10. Implemented by Other Partner | PO propose cancel due to NY Implemented by IndoHR | 2017-03-26
130510 | 0 | PO Released | 34689011 | A.6. TI Service | 6747589 |  |  |  |  | 6747589 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR | 2017-03-14
132678 | 0 | PO Released | 34689007 | A.6. TI Service | 6747589 |  |  |  |  | 6747589 | 9.1. Cancel PO | PO already deleted, need to re-active
132759 | 0 | PO Released | 34688900 | A.6. TI Service | 6747589 |  |  |  |  | 6747589 | 10. Implemented by Other Partner | PO propose cancel due to NY Implemented by IndoHR | 2017-04-13
134113 | 0 | PO Released | 34688773 | A.6. TI Service | 2269816 | 2017-07-31 |  |  |  | 2269816 | 1.3. eWCC submit | PO propose cancel due to NY Implemented by IndoHR | 2017-03-26
630444 | Kebalen Wetan - Kedung Kandang | PO Released | 34688136 | A.6. TI Service | 2269816 | 2017-07-22 | 2017-07-25 | 3468/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 2269816 | 1.1. eWCC approved |  | 2017-03-26
131013_130187 | - | PO Released | 34654527 | A.6. TI Service ALU | 11485500 |  |  |  |  | 11485500
130280 | Kol Sugiono | PO Released | 34654327 | 1.9.1 TI Material Delivery | 400000 | 2017-07-17 | 2017-07-19 | 1731/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-10
130145_130146 | - | PO Released | 34654088 | A.6. TI Service ALU | 11485500 |  |  |  |  | 11485500
130155_new130155 | - | PO Released | 34653988 | A.6. TI Service ALU | 9471500 |  |  |  |  | 9471500
130151_130152 | - | PO Released | 34653510 | A.6. TI Service ALU | 9471500 |  |  |  |  | 9471500
630070 | 0 | PO Released | 34644294 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR
630114 | 0 | PO Released | 34644287 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR | 2017-03-23
130174 | Udang Bangil B | PO Released | 34644282 | 1.9.1 TI Material Delivery | 400000 | 2017-07-17 | 2017-07-19 | 1730/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-26
135203 | 0 | PO Released | 34644276 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR
131539 | 0 | PO Released | 34644271 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR | 2017-05-19
131215_130061 | - | PO Released | 34618430 | A.6. TI Service ALU | 12511500 |  |  |  |  | 12511500
212637 | GOR Sudiang | PO Released | 34612109 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
213148 | Pettuadae-Turikale | PO Released | 34612098 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212147 | Site Tonasa 1 | PO Released | 34611779 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
135144_131734 | - | PO Released | 34597130 | A.6. TI Service ALU | 10416750 |  |  |  |  | 10416750
132375_130484 | - | PO Released | 34597088 | A.6. TI Service ALU | 10416750 |  |  |  |  | 10416750
132257_130387 | - | PO Released | 34597049 | A.6. TI Service ALU | 10416750 |  |  |  |  | 10416750
132189_131013 | - | PO Released | 34597024 | A.6. TI Service ALU | 10416750 |  |  |  |  | 10416750
132172_130802 | - | PO Released | 34596995 | A.6. TI Service ALU | 10416750 |  |  |  |  | 10416750
132302_132301 | - | PO Released | 34596944 | A.6. TI Service ALU | 10416750 |  |  |  |  | 10416750
132275_130384 | - | PO Released | 34596679 | A.6. TI Service ALU | 10416750 |  |  |  |  | 10416750
130681_130181 | - | PO Released | 34596638 | A.6. TI Service ALU | 10416750 |  |  |  |  | 10416750
130542_130585 | - | PO Released | 34596605 | A.6. TI Service ALU | 10416750 |  |  |  |  | 10416750
132568_137003 | - | PO Released | 34596565 | A.6. TI Service ALU | 10416750 |  |  |  |  | 10416750
|  | PO Released | 34595075 |  | 1087500 |  |  |  |  | 1087500
|  | PO Released | 34538633 |  | 400000 |  |  |  |  | 400000
132385 | DMT TUBAN 3 | PO Released | 34538632 | 1.9.1 TI Material Delivery | 400000 | 2017-07-27 | 2017-07-28 | 4251/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved | Double PO LMD | 2017-05-22
|  | PO Released | 34538619 |  | 400000 |  |  |  |  | 400000
|  | PO Released | 34538603 |  | 400000 |  |  |  |  | 400000
130584 | Pahlawan - Semanding | PO Released | 34538576 | 1.9.1 TI Material Delivery | 400000 | 2017-07-27 | 2017-07-28 | 4327/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved | Double PO LMD | 2017-05-22
131939 | LERAN KULON GF | PO Released | 34538570 | 1.9.1 TI Material Delivery | 400000 | 2017-07-27 | 2017-07-28 | 4314/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved | Double PO LMD | 2017-05-22
130120 | Jambangan Kebon - Jambangan I | PO Released | 34538504 | 1.9.1 TI Material Delivery | 400000 | 2017-07-22 | 2017-07-24 | 2632/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-15
631074 | - | PO Released | 34538323 | 1.9.1 TI Material Delivery | 400000 | 2017-07-22 | 2017-07-28 | 4174/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-19
631050 | - | PO Released | 34538320 | 1.9.1 TI Material Delivery | 400000 | 2017-07-22 | 2017-07-28 | 4166/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-19
132776 | DCS_PANYURAN | PO Released | 34532136 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR
133172 | Widang-Babat | PO Released | 34532128 | 1.9.1 TI Material Delivery | 400000 | 2017-07-19 | 2017-07-28 | 4049/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-22
131938 | Karangrejo Palang_GF | PO Released | 34532116 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4312/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-22
130583 | NURAMA-TUBAN | PO Released | 34532100 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-25 | 3341/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-22
132717 | DMT_STO TUBAN | PO Released | 34532094 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR | 2017-05-22
132706 | Perum Semen Gresik T | PO Released | 34532086 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4198/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-22
130175 | Basuki Rahmad Tuban | PO Released | 34532073 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-24 | 2635/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-22
132355 | DMT_Tuban Relok | PO Released | 34532058 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR | 2017-05-22
132712 | IBS_Ronggo Mulyo | PO Released | 34532028 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR
133619 | STI Tuban | PO Released | 34532024 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 2.2. NY create in eWCC
131937 | SugihWaras_GF | PO Released | 34532012 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4311/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-22
132723 | BLANDONGAN | PO Released | 34532010 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4199/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-22
131441 | Karang Rejo - Gempol | PO Released | 34532005 | 1.9.1 TI Material Delivery | 400000 | 2017-07-19 | 2017-07-21 | 2246/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-10
133040 | ISAT_WAGE_PERMAI | PO Released | 34532000 | 1.9.1 TI Material Delivery | 400000 | 2017-07-19 | 2017-07-28 | 4046/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-10
133595 | IBS_BANGIL | PO Released | 34531996 | 1.9.1 TI Material Delivery | 400000 | 2017-07-19 | 2017-07-28 | 4036/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-10
131327 | PURWOSARI | PO Released | 34531992 | 1.9.1 TI Material Delivery | 400000 | 2017-07-19 | 2017-07-21 | 2241/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-10
131523 | Gempol Pandaan | PO Released | 34531987 | 1.9.1 TI Material Delivery | 400000 | 2017-07-19 | 2017-07-21 | 2247/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-10
130841 | IT - BUDURAN | PO Released | 34531983 | 1.9.1 TI Material Delivery | 400000 | 2017-07-19 | 2017-07-21 | 2237/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-10
132382 | BANGIL | PO Released | 34531979 | 1.9.1 TI Material Delivery | 400000 | 2017-07-19 | 2017-07-21 | 2263/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-10
132306 | ISAT Bakalan Pasuruan | PO Released | 34531976 | 1.9.1 TI Material Delivery | 400000 | 2017-07-19 | 2017-07-28 | 4241/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-10
132571 | ISAT_KRATON | PO Released | 34531973 | 1.9.1 TI Material Delivery | 400000 | 2017-07-19 | 2017-07-28 | 4052/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-10
130590 | XL - NGERONG | PO Released | 34531970 | 1.9.1 TI Material Delivery | 400000 | 2017-07-19 | 2017-07-21 | 2232/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-10
133809 | Protelindo Ruko Semarang | PO Released | 34531967 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR
133797 | Protelindo_Petemon | PO Released | 34531965 | 1.9.1 TI Material Delivery | 400000 | 2017-07-19 | 2017-07-28 | 4039/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-23
133777 | Protelindo Kalijaten_GF | PO Released | 34531961 | 1.9.1 TI Material Delivery | 400000 | 2017-07-19 | 2017-07-28 | 4038/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-23
133815 | Protelindo_Simorukun | PO Released | 34531959 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4040/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-14
630506 | XLPandaan | PO Released | 34531948 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4157/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-23
630473 | Pandaan | PO Released | 34531947 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4177/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-24
130023 | BRATANGGDWROMO | PO Released | 34531884 | 1.9.1 TI Material Delivery | 400000 | 2017-07-17 | 2017-07-19 | 1720/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-17
132863 | NDK_Kedungrejo | PO Released | 34531879 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4205/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
131394 | Tropodo Niaga - Waru B | PO Released | 34531872 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-26 | 3549/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-04-11
130742 | XL - TAMBAK PINGGIR | PO Released | 34531863 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-25 | 3349/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-10
130021 | BUNGTOMOGUBENG | PO Released | 34531847 | 1.9.1 TI Material Delivery | 400000 | 2017-07-22 | 2017-07-24 | 2631/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-16
130136 | JTSD002A-Sidoarjo Gedangan | PO Released | 34531842 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-25 | 3303/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-27
130851 | PEPELEGI | PO Released | 34531837 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-25 | 3360/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
130512 | 0 | PO Released | 34531830 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR
130020 | Juwingan Gubeng | PO Released | 34531824 | 1.9.1 TI Material Delivery | 400000 | 2017-07-22 | 2017-07-24 | 2630/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-17
132934 | STP_Gedangan Wetan | PO Released | 34531820 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4206/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
130518 | LABANSRISUTORJ | PO Released | 34531814 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-25 | 3338/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-04-07
131709 | Komet Aloha | PO Released | 34531809 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-26 | 3570/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
132935 | IBS_Kepuh Kiriman | PO Released | 34531803 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4207/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
131486 | Wedoro - Waru B | PO Released | 34531796 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-26 | 3552/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-04-11
130137 | SEMAMPIRSEDATI | PO Released | 34531791 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-24 | 2633/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-20
130067 | Candi Lontar | PO Released | 34531785 | 1.9.1 TI Material Delivery | 400000 | 2017-07-19 | 2017-07-21 | 2217/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-10
131666 | TELCOINDO - KEPUH | PO Released | 34531779 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-26 | 3561/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-23
133136 | IBS_PABEAN | PO Released | 34531773 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4189/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
133050 | IBS_Makro Pepelegi | PO Released | 34531766 | 1.9.1 TI Material Delivery | 400000 | 2017-07-19 | 2017-07-28 | 4047/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
132876 | NTS_SEDAP MALAM | PO Released | 34531758 | 1.9.1 TI Material Delivery | 400000 | 2017-07-19 | 2017-07-28 | 4056/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
130131 | JTSD001A-Sidoarjo Aloha | PO Released | 34531754 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-25 | 3299/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-27
133100 | SAWOTRATAP_GF | PO Released | 34531748 | 1.9.1 TI Material Delivery | 400000 | 2017-07-19 | 2017-07-28 | 4048/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
131602 | KEBON AGUNG | PO Released | 34531739 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-26 | 3558/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-02
132555 | Axis_Ngasem | PO Released | 34531733 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR
131676 | PARE | PO Released | 34531726 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR
132757 | KEDUNG PEDARINGAN | PO Released | 34531720 | 1.9.1 TI Material Delivery | 400000 | 2017-07-19 | 2017-07-28 | 4055/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-02
631058 | SEKOTO | PO Released | 34531714 | 1.9.1 TI Material Delivery | 400000 | 2017-07-27 | 2017-07-28 | 4172/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-21
133917 | SUGATEN_GF | PO Released | 34531709 | 1.9.1 TI Material Delivery | 400000 | 2017-07-19 | 2017-07-28 | 4044/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-10
133921 | KARTOHARJO_GF | PO Released | 34531703 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4187/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-10
132372 | XL_Winongo Madiun | PO Released | 34531697 | 1.9.1 TI Material Delivery | 400000 | 2017-07-25 | 2017-07-28 | 4247/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-10
132352 | DMT_STO Telkom Ponorogo | PO Released | 34531690 | 1.9.1 TI Material Delivery | 400000 | 2017-07-19 | 2017-07-28 | 4070/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
132375 | DMT_Ds.Kranggan (Simpang) | PO Released | 34531685 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR
130241 | Garuda - Pakis Aji | PO Released | 34531679 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-24 | 2636/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-15
133244 | KENITEN PONOROGO | PO Released | 34531672 | 1.9.1 TI Material Delivery | 400000 | 2017-07-19 | 2017-07-28 | 4050/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
130599 | Gondanglegi Wetan - Gondanglegi | PO Released | 34531665 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-25 | 3342/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-02
133403 | XL_Mojoroto | PO Released | 34531658 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR
131679 | TSEL INKA DCS 1 | PO Released | 34531646 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR
131852 | DMT_KEDUNGWARU | PO Released | 34531640 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-28 | 4086/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
130690 | Madukoro - Lawang | PO Released | 34531634 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-25 | 3345/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-02
131695 | XL - ARJOWINANGUN PACITAN | PO Released | 34531626 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-26 | 3568/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
131429 | KH. Dewantoro - Badas | PO Released | 34531620 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-21 | 2244/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
132369 | IBS_Brotonegoro | PO Released | 34531612 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-28 | 4074/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
131444 | Sidodadi - Kepanjen B | PO Released | 34531606 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-26 | 3551/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-02
132691 | XL_LANGENHARJO KEDIRI 2 | PO Released | 34531598 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR
131905 | KARANGDUREN | PO Released | 34531591 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-28 | 4087/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-02
133679 | Kutoanyar | PO Released | 34531583 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-28 | 4037/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
130767 | XL - SEMEN KEDIRIi | PO Released | 34531576 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR
134266 | KNU_3G Panggungrejo Kepanjen | PO Released | 34531568 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4182/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
132377 | XL_Universitas Kediri | PO Released | 34531562 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR
133927 | MANISREJO_GF | PO Released | 34531554 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-28 | 4045/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-10
631045 | ISATPARE | PO Released | 34531548 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4005/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-25
131728 | PELEM_KDR | PO Released | 34531541 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR
131645 | ISAT - PONOROGO | PO Released | 34531534 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-21 | 2252/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
132533 | Nglames_GF | PO Released | 34531527 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4252/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-22
132367 | DMT_Ponorogo 4 Reloc | PO Released | 34531517 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-28 | 4072/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
132634 | ISAT_KEDIRI_CITY | PO Released | 34531510 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4193/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
133450 | IBS_Ploso Pacitan | PO Released | 34531503 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-28 | 4035/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
131738 | REMBANG_KDR | PO Released | 34531496 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4302/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
131683 | Ngurah Rai - Tulungagung B | PO Released | 34531485 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-26 | 3563/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-06-07
131684 | Ploso Kandang - Kedung Waru C | PO Released | 34531477 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-21 | 2254/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
631069 | Gondang Legi | PO Released | 34531466 | 1.9.1 TI Material Delivery | 400000 | 2017-07-22 | 2017-07-28 | 4173/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-17
130379 | Munginsidi - Magetan | PO Released | 34531457 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-25 | 3320/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-10
132697 | LAWANG | PO Released | 34531449 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4197/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-18
131845 | Ngronggo | PO Released | 34531438 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4307/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-19
134075 | B2S_Protelindo Balowerti | PO Released | 34531429 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4179/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
132665 | PAGEDANGAN_GF | PO Released | 34531419 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4195/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-19
132361 | Turen | PO Released | 34531411 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4243/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-02
131430 | Gede - Pare | PO Released | 34531403 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR
132030 | Ploso_Pacitan_GF | PO Released | 34531399 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-28 | 4066/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
130710 | PROTELINDO - PAKISAJI | PO Released | 34531393 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-25 | 3347/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-18
631057 | STO PARE | PO Released | 34531388 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-28 | 4008/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-24
630082 | STO TULUNGAGUNG | PO Released | 34531380 | 1.9.1 TI Material Delivery | 400000 | 2017-07-22 | 2017-07-28 | 4019/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
131696 | PONOROGO | PO Released | 34531374 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-26 | 3569/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
132587 | Axis_Bujel | PO Released | 34531367 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4192/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-19
132051 | Susuan Gampangrejo_GF | PO Released | 34531361 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4239/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-19
130977 | XL - GUDANG GARAM KEDIRI | PO Released | 34531348 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR | 2017-05-19
132560 | NAMBAAN | PO Released | 34531342 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR
630487 | GEDANGSEWU TULUNGAGUNG | PO Released | 34531336 | 1.9.1 TI Material Delivery | 400000 | 2017-07-22 | 2017-07-28 | 4156/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-12
133715 | Stadion Brawijaya Kediri | PO Released | 34531329 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR
133153 | STP_Bedali Lawang | PO Released | 34531322 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4191/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-02
131512 | DEMETA - PONOROGO 2 | PO Released | 34531318 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-26 | 3555/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-19
130522 | Inspeksi Pengairan - Mojoroto | PO Released | 34531311 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR
134249 | Indosat_Kelayatan | PO Released | 34531309 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4180/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-02
132390 | DMT_Ponorogo 3 | PO Released | 34531305 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-28 | 4075/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-19
630343 | IBS Mojorejo | PO Released | 34531302 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-28 | 4025/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-20
131624 | KARTOHARJO | PO Released | 34531299 | 1.9.1 TI Material Delivery | 400000 | 2017-07-25 | 2017-07-26 | 3559/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-10
132664 | SIMPANG MATARAM_GF | PO Released | 34531295 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4194/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-02
132276 | LAHAN IBU SUNARTI | PO Released | 34531291 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4240/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-02
132848 | DMT_Tanjung Pagu | PO Released | 34531289 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4204/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-19
131911 | DMT_STO PACITAN | PO Released | 34531286 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-28 | 4088/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-19
132275 | BABADAN | PO Released | 34531281 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-28 | 4067/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-19
133919 | Greja Menara Advent RT | PO Released | 34531279 | 1.9.1 TI Material Delivery | 400000 | 2017-07-22 | 2017-07-28 | 4186/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-22
131846 | SEMEN_KDR | PO Released | 34531277 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR | 2017-05-19
130839 | NGLAMES | PO Released | 34531273 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-25 | 3357/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-22
133356 | XL_Pesantren Kediri | PO Released | 34531271 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR
132552 | ISAT_DOKO GAMPENGREJO | PO Released | 34531270 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR
132551 | NTS_Lirboyo | PO Released | 34531269 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4253/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-19
130625 | Masjid - Gampengrejo | PO Released | 34531268 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-25 | 3344/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-19
130849 | JIWAN | PO Released | 34531267 | 1.9.1 TI Material Delivery | 400000 | 2017-07-22 | 2017-07-25 | 3359/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-22
134273 | Ponorogo | PO Released | 34531266 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-28 | 4034/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-19
630086 | STP Pahitan Wetan | PO Released | 34531264 | 1.9.1 TI Material Delivery | 400000 | 2017-07-22 | 2017-07-28 | 4020/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
131365 | Srikaton - Kartoharjo | PO Released | 34531263 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-26 | 3548/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-22
131686 | Pilang Mulya - Kartoharjo | PO Released | 34531262 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-26 | 3565/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-22
631088 | TULUNGREJO MALANG TBG | PO Released | 34531259 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4015/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-26
132368 | DMT_Siman / Ponorogo 5 | PO Released | 34531258 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-28 | 4073/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-06-07
133614 | Supersemar ex Repeat | PO Released | 34531257 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-26 | 3576/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
132554 | ISAT_Ngadismo_kediri | PO Released | 34531256 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR
631090 | KNU Trunojoyo Malang | PO Released | 34531255 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4016/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-25
132556 | IBS_Kepanjen | PO Released | 34531254 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4254/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-22
132629 | DMT Tulungagung 3 | PO Released | 34531252 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-28 | 4053/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-06-08
630119 | B2S Vitcom Ruko Gajah Mada | PO Released | 34531251 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-28 | 4021/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-22
631012 | Ketindan lawang | PO Released | 34531250 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4161/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-23
631089 | SUPRIYADI MALANG | PO Released | 34531249 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4175/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-26
631000 | ISAT-Tlogomas | PO Released | 34531247 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4158/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-22
630301 | Jenangan PTI | PO Released | 34531246 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-28 | 4024/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-20
630292 | Tambak Bayan | PO Released | 34531245 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-28 | 4023/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-20
631091 | STT AD | PO Released | 34531242 | 1.9.1 TI Material Delivery | 400000 | 2017-07-25 | 2017-07-28 | 4176/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-26
631053 | Gayam Mojoroto | PO Released | 34531240 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4169/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-23
131779 | ISAT Magetan | PO Released | 34531239 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4303/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-22
631083 | KEDIRI1 | PO Released | 34531235 | 1.9.1 TI Material Delivery | 400000 | 2017-07-22 | 2017-07-28 | 4013/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
130399 | Gatot Subroto - Turen | PO Released | 34531233 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-25 | 3327/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-10
131736 | Katang | PO Released | 34531229 | 1.9.1 TI Material Delivery | 400000 | 2017-07-25 | 2017-07-28 | 4301/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-18
130949 | XL - PATIHAN WETAN | PO Released | 34531223 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-21 | 2239/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-06-08
130390 | Basuki Rahmad - Pacitan | PO Released | 34531218 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-25 | 3325/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
132730 | BANGUNSARI | PO Released | 34531212 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-28 | 4054/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-18
132574 | MANISRENGGO KOTA KEDIRI | PO Released | 34531206 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR | 2017-05-18
130884 | XL - PANDEAN MADIUN | PO Released | 34531199 | 1.9.1 TI Material Delivery | 400000 | 2017-07-25 | 2017-07-26 | 3547/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-22
132833 | IBS_Tambran | PO Released | 34531191 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4201/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-22
631002 | Sinabung | PO Released | 34531184 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4003/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-18
131552 | Sultan Hasanudin - Kedungwaru D | PO Released | 34531180 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-21 | 2249/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-18
131635 | SUMBER PORONG | PO Released | 34531175 | 1.9.1 TI Material Delivery | 400000 | 2017-07-22 | 2017-07-26 | 3560/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-15
130152 | Asrama TNI KODIM 0809 | PO Released | 34531165 | 1.9.1 TI Material Delivery | 400000 | 2017-07-22 | 2017-07-25 | 3308/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-27
131564 | ISAT - DUNGUS MADIUN | PO Released | 34531152 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-26 | 3557/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-22
631019 | Kandya'an | PO Released | 34531142 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4163/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-22
130145 | Tawang Sari - Kartoharjo | PO Released | 34531133 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-25 | 3304/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-27
131910 | Sambong | PO Released | 34531130 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4310/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-06-07
130876 | XL - MAGETAN | PO Released | 34531127 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-26 | 3544/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-22
130381 | Merapi - Ponorogo | PO Released | 34531123 | 1.9.1 TI Material Delivery | 400000 | 2017-07-22 | 2017-07-25 | 3322/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
130240 | Raya Jatikerto-Kromengan | PO Released | 34531122 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-25 | 3311/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-27
131855 | JIWAN | PO Released | 34531120 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4308/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-26
130680 | Dusun Gempol - Sumber Gempol B | PO Released | 34531119 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-21 | 2234/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-06-07
130485 | Indrokiloselatan-Lawang | PO Released | 34531117 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-25 | 3331/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-10
132559 | PAMENANG | PO Released | 34531115 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR
131844 | PROLIMAN | PO Released | 34531113 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR
131688 | Mliwis - Mangunharjo | PO Released | 34531112 | 1.9.1 TI Material Delivery | 400000 | 2017-07-25 | 2017-07-26 | 3567/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-12
131697 | MADIUN_CITY | PO Released | 34531109 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR | 2017-05-12
130645 | XL - GEDANG SEWU | PO Released | 34531107 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR
130576 | Dahlia - Boyolangu | PO Released | 34531103 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-21 | 2231/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
131685 | Taman Praja - Taman B | PO Released | 34531102 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-26 | 3564/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-12
131551 | Panglima Sudirman - Tulungagung D | PO Released | 34531099 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-21 | 2248/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
130382 | Siman - Siman | PO Released | 34531098 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-25 | 3323/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
130154 | Kantor Pos Kediri-Mrican | PO Released | 34531096 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR | 2017-03-27
131628 | LSK - SIDOHARJO PACITAN | PO Released | 34531093 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-21 | 2251/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
131735 | Ngronggo Kota | PO Released | 34531092 | 1.9.1 TI Material Delivery | 400000 | 2017-07-25 | 2017-07-26 | 3571/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-06-08
132373 | ISAT PATIHAN | PO Released | 34531091 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4248/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-12
130881 | XL - MANISREJO | PO Released | 34531090 | 1.9.1 TI Material Delivery | 400000 | 2017-07-25 | 2017-07-26 | 3546/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-12
631055 | UNIVKEDIRI | PO Released | 34531088 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4170/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-06-07
130147 | Aloon-aloon Timur - Mangunharjo | PO Released | 34531087 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-25 | 3305/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-27
130481 | Klotok - Mojoroto | PO Released | 34531085 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR
134073 | Ponpes Lirboyo | PO Released | 34531084 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4178/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-23
631026 | Isat_BandarLor | PO Released | 34531082 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR | 2017-05-17
134090 | ISAT_KEDIRI | PO Released | 34531080 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR
133740 | Protelindo LANAL Malang | PO Released | 34531078 | 1.9.1 TI Material Delivery | 400000 | 2017-07-22 | 2017-07-28 | 4184/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-22
131780 | Sukowinangun | PO Released | 34531076 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4306/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-12
130759 | XL - BULULAWANG | PO Released | 34531075 | 1.9.1 TI Material Delivery | 400000 | 2017-07-22 | 2017-07-25 | 3351/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-12
132297 | XL_Tiron_Madiun | PO Released | 34531074 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR | 2017-05-12
131510 | NURAMA - YOS SUDARSO | PO Released | 34531071 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-26 | 3554/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-12
630251 | Nambangan Kidul | PO Released | 34531070 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-28 | 4022/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-22
631054 | Ngampel | PO Released | 34531068 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4007/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-21
130148 | Sunan Bonang - Kartoharjo | PO Released | 34531064 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-25 | 3307/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-27
631080 | Tidar | PO Released | 34531063 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4011/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-19
631052 | XL Jongbiru | PO Released | 34531061 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-28 | 4168/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-21
631027 | Tegal Gondo | PO Released | 34531059 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4004/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-20
631078 | Dinoyo ML | PO Released | 34531058 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4010/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-19
631086 | HUBDAM Malang | PO Released | 34531054 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4014/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-26
631048 | IMAM BONJOL TBG | PO Released | 34531053 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4006/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-20
631081 | 3G-A. YANI MALANG | PO Released | 34531051 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4012/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-20
131687 | Joyodanu - Taman C | PO Released | 34531050 | 1.9.1 TI Material Delivery | 400000 | 2017-07-25 | 2017-07-26 | 3566/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-12
131672 | Thamrin - Kartoharjo E | PO Released | 34531046 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-26 | 3562/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-12
130302 | Raya Mulyorejo-Sukun | PO Released | 34531045 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-25 | 3318/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-19
130142 | Mayjen Panjaitan-Taman | PO Released | 34531044 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR
|  | PO Released | 34531041 |  | 400000 |  |  |  |  | 400000
134292 | RST. Soepraoen Malang | PO Released | 34531037 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4183/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-12
132740 | DMT Mendalawangi | PO Released | 34531034 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4200/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-12
631043 | RAMAYANA KEDIRI | PO Released | 34531032 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4165/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
130619 | KH. Malik Dalam - Kedung Kandang | PO Released | 34531030 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-25 | 3343/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-12
132836 | Axis_Dirgantara Auri | PO Released | 34531029 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4203/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-12
134285 | B2S_Protelindo_Banjar Kidul | PO Released | 34531027 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR
130444 | Kebalen Wetan - Kedung Kandang | PO Released | 34531024 | 1.9.1 TI Material Delivery | 400000 | 2017-07-18 | 2017-07-19 | 1734/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-04-05
132695 | DMT_Kedung Kandang | PO Released | 34531021 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4196/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-12
134065 | CEMARA7 | PO Released | 34531020 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4188/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-06-07
130484 | Hayam Wuruk - Kediri B | PO Released | 34531019 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-25 | 3330/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
131751 | XL Parang Argo | PO Released | 34531017 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-28 | 4085/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-18
631014 | TAMAN SULFAT | PO Released | 34531014 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4162/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
130293 | LA.Sucipto - Blimbing | PO Released | 34531013 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-21 | 2225/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
130275 | Klojen | PO Released | 34531011 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-25 | 3312/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
130276 | Mas FM | PO Released | 34531009 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-21 | 2222/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
133290 | XL_Arjosari | PO Released | 34531007 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-28 | 4051/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-06-07
130999 | XL - SIDORAHAYU | PO Released | 34531003 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-21 | 2240/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-06-07
133887 | Protelindo_Soekarno Hatta | PO Released | 34531002 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-28 | 4042/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
134076 | B2S_Protelindo Ngadirejo | PO Released | 34531001 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-28 | 4033/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
130474 | Raya Wendit Timur - Pakis | PO Released | 34530998 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-21 | 2227/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
130164 | Mulyo Agung Dau | PO Released | 34530996 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-21 | 2219/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-03-27
131907 | SUNGKONO ML | PO Released | 34530995 | 1.9.1 TI Material Delivery | 400000 | 2017-07-24 | 2017-07-28 | 4309/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
131546 | KH.Wahid Hasyim - Mojoroto | PO Released | 34530993 | 1.9.1 TI Material Delivery | 400000 |  |  |  |  | 400000 | 9.1. Cancel PO | PO propose cancel due to NY Implemented by IndoHR
130279 | Brigjen Katamso - Klojen | PO Released | 34530989 | 1.9.1 TI Material Delivery | 400000 | 2017-07-20 | 2017-07-21 | 2223/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
133401 | IBS_Kediri Town | PO Released | 34530984 | 1.9.1 TI Material Delivery | 400000 | 2017-07-13 | 2017-07-16 | 1685/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-06-07
132553 | Axis_Kali Ombo | PO Released | 34530982 | 1.9.1 TI Material Delivery | 400000 | 2017-07-19 | 2017-07-21 | 2265/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-06-07
132294 | SUKUN | PO Released | 34530979 | 1.9.1 TI Material Delivery | 400000 | 2017-07-19 | 2017-07-28 | 4068/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-06-08
130291 | Kerapu-Blimbing | PO Released | 34530978 | 1.9.1 TI Material Delivery | 400000 | 2017-07-19 | 2017-07-21 | 2224/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
131747 | KENARI | PO Released | 34530975 | 1.9.1 TI Material Delivery | 400000 | 2017-07-17 | 2017-07-19 | 1757/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
133874 | Watu Mujur_GF | PO Released | 34530974 | 1.9.1 TI Material Delivery | 400000 | 2017-07-19 | 2017-07-28 | 4041/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 400000 | 1.1. eWCC approved |  | 2017-05-17
62690 | Pasar Baru OKU | PO Released | 34530971 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
62056 | Veteran Jaya | PO Released | 34530970 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
61020 | Simpang Talang Dukun - Sungai Pinang | PO Released | 34530968 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
62115 | Jua Jua - Kayu Agung | PO Released | 34530965 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
62078 | Paku Sengkunyit-Martapura | PO Released | 34530964 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
61103 | Lintas Timur - Muara baru | PO Released | 34530963 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
60578 | Raya Dr. Sutomo - Tanjung Kemala | PO Released | 34530958 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
60208 | Lintas Sumatera - Kota Baru | PO Released | 34530953 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
62067 | TANJUNG RAJA2 (STO Tj Raja) | PO Released | 34530951 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
62428 | DMT-Simpang Timbangan | PO Released | 34530949 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
61627 | Batu Raja Reapeater 2 | PO Released | 34530946 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
62192 | Indosat-PASAR_INDERALAYA | PO Released | 34530944 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
62105 | Kemala raja-Baturaja Timur | PO Released | 34530942 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
61593 | Batu raja 3 | PO Released | 34530940 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
60138 | A. Yani 160 Air Karang - Tanjung Baru | PO Released | 34530938 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
61731 | XL-Dan Bekang Martapura | PO Released | 34530937 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
60139 | Kol. H. Burlian - Pusar | PO Released | 34530935 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
61762 | ISAT-Kayu Agung | PO Released | 34530932 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
62094 | Sukadana- Kayu Agung | PO Released | 34530931 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
62702 | Martadinata Lahat | PO Released | 34530930 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
60144 | Kapten Satar - Kota Baru | PO Released | 34530929 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
62047 | Protelindo_Kayu Agung | PO Released | 34530925 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
61736 | Protelindo- Indralaya | PO Released | 34530924 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
60267 | Tasik Dusun V - Indralaya | PO Released | 34530922 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
62127 | Sukajadi baturaja | PO Released | 34530920 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
62705 | Sukadana KayuAgung | PO Released | 34530919 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
61594 | Martapura | PO Released | 34530918 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
61553 | Indosat - Tanjung Raja | PO Released | 34530916 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
62092 | Tanjung Raja- Tanjung Raja | PO Released | 34530915 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
62722 | Tanjung Rancing | PO Released | 34530913 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
60151 | Demang Hamid LK.V - Paku | PO Released | 34530908 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
62104 | Sarang elang | PO Released | 34530900 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
62126 | Keromongan | PO Released | 34530896 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
62065 | STO LAHAT RELOK | PO Released | 34530895 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
61620 | Lahat | PO Released | 34530893 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
60160 | Mahkota Raja - Timbangan | PO Released | 34530890 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
61520 | Ogan - Kemala Jaya | PO Released | 34530888 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
62168 | Kota Baru Barat - Martapura | PO Released | 34530886 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
60595 | A. Yani - Baturaja | PO Released | 34530885 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
62075 | Protelindo_Martapura | PO Released | 34530881 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
62071 | Sungai Pinang-1 | PO Released | 34530874 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
62229 | Pagar_Agung | PO Released | 34530873 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
62138 | Pasar Lama Lahat | PO Released | 34530871 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
62043 | Kapten tendean Baturaja | PO Released | 34530870 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
62117 | Keluarga | PO Released | 34530868 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
62093 | Seri Jabo- Sungai Pinang | PO Released | 34530867 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
62095 | Talang_Jawa_Lahat | PO Released | 34530862 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
60582 | Lintas Muara Enim - Batu Kuning | PO Released | 34530858 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
60585 | Padat Karya - Sekarjaya | PO Released | 34530856 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
60587 | Imam Bonjol - Sukaraja | PO Released | 34530855 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
62044 | Kompleks Mutiara Indah | PO Released | 34530852 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
62499 | Simanjuntak | PO Released | 34530851 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
62651 | Suka Raya Batu Raja | PO Released | 34530836 | 1.9.1 TI Material Delivery SouthSum | 400000 |  |  |  |  | 400000
134249 | Indosat_Kelayatan | PO Released | 34457004 | A.6. TI Service | 6747589 | 2017-07-24 | 2017-07-28 | 4181/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-20
131747 | KENARI | PO Released | 34456950 | A.6. TI Service | 6747589 | 2017-07-15 | 2017-07-28 | 4084/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-04-08
130444 | Kebalen Wetan - Kedung Kandang | PO Released | 34456916 | A.6. TI Service | 6747589 | 2017-07-15 | 2017-07-19 | 1735/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-04-05
130174 | Udang Bangil B | PO Released | 34456798 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
62702 | Martadinata Lahat | PO Released | 34456663 | A.6. TI Service SouthSum | 1769845 | 2017-07-22 | 2017-07-25 | 3178/eWCC/H3I/INH/E3/VII/2017 | 2017-07-01 | 1769845 | 1.1. eWCC approved |  | 2017-03-23
62705 | Sukadana KayuAgung | PO Released | 34456647 | A.6. TI Service SouthSum | 1769845 |  |  |  |  | 1769845 | 2.10. Wrong Ewcc Status | Wrong Status in eWCC | 2017-03-10
62722 | Tanjung Rancing | PO Released | 34456632 | A.6. TI Service SouthSum | 1769845 |  |  |  |  | 1769845 | 2.10. Wrong Ewcc Status | Wrong Status in eWCC | 2017-03-26
62690 | Pasar Baru OKU | PO Released | 34456616 | A.6. TI Service SouthSum | 1769845 |  |  |  |  | 1769845 | 4.7. Waiting Doc MSFI |  | 2017-03-26
62651 | Suka Raya Batu Raja | PO Released | 34456503 | A.6. TI Service SouthSum | 1769845 |  |  |  |  | 1769845 | 2.10. Wrong Ewcc Status | Wrong Status in eWCC | 2017-03-18
60144 | Kapten Satar - Kota Baru | PO Released | 34456302 | A.6. TI Service SouthSum | 7247174 |  |  |  |  | 7247174 | 8.3. NY MSFI App |  | 2017-03-24
62065 | STO LAHAT RELOK | PO Released | 34456282 | A.6. TI Service SouthSum | 8779878 |  |  |  |  | 8779878 | 8.3. NY MSFI App |  | 2017-03-24
130518 | LABANSRISUTORJ | PO Released | 34456278 | A.6. TI Service | 6747589 |  |  |  |  | 6747589 | 8.3. NY MSFI App |  | 2017-04-07
61620 | Bali Telekom - Lahat | PO Released | 34456248 | A.6. TI Service SouthSum | 7247174 |  |  |  |  | 7247174 | 8.3. NY MSFI App |  | 2017-03-23
62229 | Pagar Agung | PO Released | 34456216 | A.6. TI Service SouthSum | 8779878 |  |  |  |  | 8779878 | 8.3. NY MSFI App |  | 2017-03-24
62138 | Pasar Lama Lahat | PO Released | 34456195 | A.6. TI Service SouthSum | 8779878 |  |  |  |  | 8779878 | 2.10. Wrong Ewcc Status | Wrong Status in eWCC | 2017-03-23
62117 | Keluarga | PO Released | 34456165 | A.6. TI Service SouthSum | 8779878 |  |  |  |  | 8779878 | 8.3. NY MSFI App |  | 2017-04-27
62095 | Talang_Jawa_Lahat | PO Released | 34456118 | A.6. TI Service SouthSum | 8779878 |  |  |  |  | 8779878 | 8.3. NY MSFI App |  | 2017-03-24
61020 | Simpang Talang Dukun - Sungai Pinang | PO Released | 34456097 | A.6. TI Service SouthSum | 7247174 | 2017-07-22 | 2017-07-25 | 3170/eWCC/H3I/INH/E3/VII/2017 | 2017-07-01 | 7247174 | 1.1. eWCC approved |  | 2017-03-24
62115 | Jua Jua - Kayu Agung | PO Released | 34456078 | A.6. TI Service SouthSum | 8779878 |  |  |  |  | 8779878 | 4.7. Waiting Doc MSFI |  | 2017-03-26
61103 | Lintas Timur - Muara baru | PO Released | 34456058 | A.6. TI Service SouthSum | 8779878 |  |  |  |  | 8779878 | 4.7. Waiting Doc MSFI |  | 2017-03-27
62067 | TANJUNG RAJA2 | PO Released | 34456041 | A.6. TI Service SouthSum | 8779878 | 2017-07-22 | 2017-07-25 | 3173/eWCC/H3I/INH/E3/VII/2017 | 2017-07-01 | 8779878 | 1.1. eWCC approved |  | 2017-03-23
62428 | Timbangan | PO Released | 34456021 | A.6. TI Service SouthSum | 8779878 | 2017-07-22 | 2017-07-25 | 3175/eWCC/H3I/INH/E3/VII/2017 | 2017-07-01 | 8779878 | 1.1. eWCC approved |  | 2017-03-21
62192 | Indosat-PASAR_INDERALAYA | PO Released | 34456002 | A.6. TI Service SouthSum | 8779878 |  |  |  |  | 8779878 | 2.10. Wrong Ewcc Status | Wrong Status in eWCC | 2017-03-23
61762 | ISAT-KAYU AGUNG | PO Released | 34455983 | A.6. TI Service SouthSum | 7247174 |  |  |  |  | 7247174 | 4.7. Waiting Doc MSFI |  | 2017-03-27
62094 | Sukadana- Kayu Agung | PO Released | 34455962 | A.6. TI Service SouthSum | 7247174 |  |  |  |  | 7247174 | 2.10. Wrong Ewcc Status | Wrong Status in eWCC | 2017-03-26
62047 | Protelindo_Kayu Agung | PO Released | 34455944 | A.6. TI Service SouthSum | 7247174 | 2017-07-22 | 2017-07-25 | 3172/eWCC/H3I/INH/E3/VII/2017 | 2017-07-01 | 7247174 | 1.1. eWCC approved |  | 2017-03-22
61736 | Protelindo- Indralaya | PO Released | 34455922 | A.6. TI Service SouthSum | 7247174 |  |  |  |  | 7247174 | 2.10. Wrong Ewcc Status | Wrong Status in eWCC | 2017-03-26
60267 | Tasik Dusun V - Indralaya | PO Released | 34455901 | A.6. TI Service SouthSum | 7247174 |  |  |  |  | 7247174 | 2.10. Wrong Ewcc Status | Wrong Status in eWCC | 2017-03-23
61553 | Tanjung Raja | PO Released | 34455878 | A.6. TI Service SouthSum | 7247174 |  |  |  |  | 7247174 | 8.3. NY MSFI App |  | 2017-03-27
62092 | Tanjung Raja- Tanjung Raja | PO Released | 34455859 | A.6. TI Service SouthSum | 8779878 |  |  |  |  | 8779878 | 2.10. Wrong Ewcc Status | Wrong Status in eWCC | 2017-03-22
60151 | Demang Hamid LK.V - Paku | PO Released | 34455841 | A.6. TI Service SouthSum | 7247174 | 2017-07-22 | 2017-07-25 | 3168/eWCC/H3I/INH/E3/VII/2017 | 2017-07-01 | 7247174 | 1.1. eWCC approved |  | 2017-03-21
60160 | Mahkota Raja - Timbangan | PO Released | 34455824 | A.6. TI Service SouthSum | 7247174 | 2017-07-22 | 2017-07-25 | 3169/eWCC/H3I/INH/E3/VII/2017 | 2017-07-01 | 7247174 | 1.1. eWCC approved |  | 2017-03-26
62071 | Sungai Pinang I | PO Released | 34455805 | A.6. TI Service SouthSum | 8779878 |  |  |  |  | 8779878 | 4.7. Waiting Doc MSFI |  | 2017-03-26
62093 | Seri Jabo- Sungai Pinang | PO Released | 34455784 | A.6. TI Service SouthSum | 8779878 |  |  |  |  | 8779878 | 2.10. Wrong Ewcc Status | Wrong Status in eWCC | 2017-03-23
62044 | Kompleks Mutiara Indah | PO Released | 34455767 | A.6. TI Service SouthSum | 7247174 |  |  |  |  | 7247174 | 2.10. Wrong Ewcc Status | Wrong Status in eWCC | 2017-03-19
62056 | Veteran Jaya | PO Released | 34455751 | A.6. TI Service SouthSum | 8922928 |  |  |  |  | 8922928 | 8.3. NY MSFI App |  | 2017-03-26
62078 | Paku Sengkunyit-Martapura | PO Released | 34455733 | A.6. TI Service SouthSum | 8779878 |  |  |  |  | 8779878 | 4.7. Waiting Doc MSFI |  | 2017-03-26
60578 | Raya Dr. Sutomo - Tanjung Kemala | PO Released | 34455715 | A.6. TI Service SouthSum | 7247174 |  |  |  |  | 7247174 | 8.3. NY MSFI App |  | 2017-04-03
60208 | Lintas Sumatera - Kota Baru | PO Released | 34455697 | A.6. TI Service SouthSum | 7247174 |  |  |  |  | 7247174 | 2.10. Wrong Ewcc Status | Wrong Status in eWCC | 2017-03-18
61627 | Batu Raja Reapeater 2 | PO Released | 34455678 | A.6. TI Service SouthSum | 7247174 |  |  |  |  | 7247174 | 2.10. Wrong Ewcc Status | Wrong Status in eWCC | 2017-03-17
62105 | Kemala Raja- Baturaja Timur | PO Released | 34455657 | A.6. TI Service SouthSum | 8779878 |  |  |  |  | 8779878 | 4.7. Waiting Doc MSFI |  | 2017-03-26
61593 | Indosat - Baturaja 3 | PO Released | 34455641 | A.6. TI Service SouthSum | 7247174 | 2017-07-22 | 2017-07-25 | 3171/eWCC/H3I/INH/E3/VII/2017 | 2017-07-01 | 7247174 | 1.1. eWCC approved |  | 2017-03-26
60138 | A. Yani 160 Air Karang - Tanjung Baru | PO Released | 34455623 | A.6. TI Service SouthSum | 7247174 |  |  |  |  | 7247174 | 8.3. NY MSFI App |  | 2017-03-26
61731 | XL-Dan Bekang Martapura | PO Released | 34455605 | A.6. TI Service SouthSum | 7247174 |  |  |  |  | 7247174 | 4.7. Waiting Doc MSFI |  | 2017-03-26
60139 | Kol. H. Burlian - Pusar | PO Released | 34455584 | A.6. TI Service SouthSum | 7247174 |  |  |  |  | 7247174 | 8.3. NY MSFI App |  | 2017-04-03
62127 | SUKAJADI BATURAJA | PO Released | 34455567 | A.6. TI Service SouthSum | 8779878 |  |  |  |  | 8779878 | 4.7. Waiting Doc MSFI |  | 2017-03-26
61594 | Indosat - Martapura | PO Released | 34455543 | A.6. TI Service SouthSum | 7247174 |  |  |  |  | 7247174 | 4.7. Waiting Doc MSFI |  | 2017-03-26
62126 | KEROMONGAN | PO Released | 34455503 | A.6. TI Service SouthSum | 8779878 |  |  |  |  | 8779878 | 4.7. Waiting Doc MSFI |  | 2017-03-30
61520 | Ogan - Kemala Jaya | PO Released | 34455483 | A.6. TI Service SouthSum | 7247174 |  |  |  |  | 7247174 | 2.10. Wrong Ewcc Status | Wrong Status in eWCC | 2017-03-18
62168 | Kota Baru Barat - Martapura | PO Released | 34455462 | A.6. TI Service SouthSum | 8779878 |  |  |  |  | 8779878 | 4.7. Waiting Doc MSFI |  | 2017-03-30
60595 | A. Yani - Baturaja | PO Released | 34454928 | A.6. TI Service SouthSum | 8779878 |  |  |  |  | 8779878 | 4.7. Waiting Doc MSFI |  | 2017-03-26
62075 | Protelindo_Martapura | PO Released | 34454923 | A.6. TI Service SouthSum | 8779878 | 2017-07-22 | 2017-07-25 | 3174/eWCC/H3I/INH/E3/VII/2017 | 2017-07-01 | 8779878 | 1.1. eWCC approved |  | 2017-03-18
62043 | Kapten tendean Baturaja | PO Released | 34454915 | A.6. TI Service SouthSum | 7247174 |  |  |  |  | 7247174 | 4.7. Waiting Doc MSFI |  | 2017-03-26
60582 | Lintas Muara Enim - Batu Kuning | PO Released | 34454906 | A.6. TI Service SouthSum | 7247174 |  |  |  |  | 7247174 | 2.10. Wrong Ewcc Status | Wrong Status in eWCC | 2017-03-17
60585 | Padat Karya - Sekarjaya | PO Released | 34454900 | A.6. TI Service SouthSum | 7247174 |  |  |  |  | 7247174 | 4.7. Waiting Doc MSFI |  | 2017-04-03
62499 | SIMANJUNTAK | PO Released | 34454866 | A.6. TI Service SouthSum | 7247174 |  |  |  |  | 7247174 | 4.7. Waiting Doc MSFI |  | 2017-03-26
631086 | HUBDAM Malang | PO Released | 34439875 | A.6. TI Service | 1615940 |  |  |  |  | 1615940 | 3.4. Need Revise PO | PO Released - change type from type A to type C; need change value from 1,615,940 become 6,747,589 | 2017-03-26
631091 | STT AD | PO Released | 34439871 | A.6. TI Service | 1615940 |  |  |  |  | 1615940 | 3.4. Need Revise PO | PO Released - change type from type A to type C; need change value from 1,615,940 become 6,747,589 | 2017-05-18
631089 | SUPRIYADI MALANG | PO Released | 34439868 | A.6. TI Service | 1615940 |  |  |  |  | 1615940 | 3.4. Need Revise PO | PO Released - change type from type A to type C; need change value from 1,615,940 become 6,747,589 | 2017-03-26
631090 | KNU Trunojoyo Malang | PO Released | 34439865 | A.6. TI Service | 1615940 |  |  |  |  | 1615940 | 3.4. Need Revise PO | PO Released - change type from type A to type C; need change value from 1,615,940 become 6,747,589 | 2017-05-27
631088 | TULUNGREJO MALANG TBG | PO Released | 34439841 | A.6. TI Service | 1615940 |  |  |  |  | 1615940 | 3.4. Need Revise PO | PO Released - change type from type A to type C; need change value from 1,615,940 become 6,747,589 | 2017-03-26
630487 | GEDANGSEWU TULUNGAGUNG | PO Released | 34439819 | A.6. TI Service | 5507895 | 2017-07-22 | 2017-07-25 | 3469/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 5507895 | 1.1. eWCC approved |  | 2017-06-14
630251 | Nambangan Kidul | PO Released | 34439782 | A.6. TI Service | 2269816 | 2017-07-22 | 2017-07-25 | 3464/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 2269816 | 1.1. eWCC approved |  | 2017-06-30
630119 | B2S Vitcom Ruko Gajah Mada | PO Released | 34439780 | A.6. TI Service | 2269816 | 2017-07-22 | 2017-07-25 | 3462/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 2269816 | 1.1. eWCC approved |  | 2017-06-09
630292 | Tambak Bayan | PO Released | 34439778 | A.6. TI Service | 2269816 | 2017-07-22 | 2017-07-25 | 3465/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 2269816 | 1.1. eWCC approved |  | 2017-06-12
630343 | IBS Mojorejo | PO Released | 34439776 | A.6. TI Service | 2269816 | 2017-07-22 | 2017-07-25 | 3467/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 2269816 | 1.1. eWCC approved |  | 2017-06-12
630301 | Jenangan PTI | PO Released | 34439773 | A.6. TI Service | 2269816 | 2017-07-22 | 2017-07-25 | 3466/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 2269816 | 1.1. eWCC approved |  | 2017-06-12
631081 | 3G-A. YANI MALANG | PO Released | 34439771 | A.6. TI Service | 2182816 | 2017-07-22 | 2017-07-25 | 3488/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 2182816 | 1.1. eWCC approved |  | 2017-06-21
631048 | IMAM BONJOL TBG | PO Released | 34439769 | A.6. TI Service | 2182816 | 2017-07-27 | 2017-07-25 | 3475/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 2182816 | 1.1. eWCC approved |  | 2017-03-21
631050 | MADYOPURO | PO Released | 34439768 | A.6. TI Service | 2182816 | 2017-07-22 | 2017-07-28 | 4167/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 2182816 | 1.1. eWCC approved |  | 2017-03-19
631078 | Dinoyo ML | PO Released | 34439765 | A.6. TI Service | 2182816 | 2017-07-22 | 2017-07-25 | 3486/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 2182816 | 1.1. eWCC approved |  | 2017-06-21
631027 | Tegal Gondo | PO Released | 34439764 | A.6. TI Service | 2182816 | 2017-07-25 | 2017-07-28 | 4164/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 2182816 | 1.1. eWCC approved |  | 2017-03-21
631074 | 3G-DIPONEGORO BATU | PO Released | 34439763 | A.6. TI Service | 2182816 | 2017-07-22 | 2017-07-25 | 3482/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 2182816 | 1.1. eWCC approved |  | 2017-06-03
631080 | Tidar | PO Released | 34439752 | A.6. TI Service | 2182816 | 2017-07-20 | 2017-07-25 | 3487/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 2182816 | 1.1. eWCC approved |  | 2017-05-30
631002 | Sinabung | PO Released | 34439749 | A.6. TI Service | 2182816 | 2017-07-25 | 2017-07-28 | 4160/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 2182816 | 1.1. eWCC approved |  | 2017-03-18
631069 | Gondang Legi | PO Released | 34439731 | A.6. TI Service | 2182816 | 2017-07-20 | 2017-07-25 | 3481/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 2182816 | 1.1. eWCC approved |  | 2017-06-21
132740 | DMT_Mendalawangi | PO Released | 34439716 | A.6. TI Service | 6747589 | 2017-07-17 | 2017-07-19 | 1936/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-05-12
131628 | LSK - SIDOHARJO PACITAN | PO Released | 34439714 | A.6. TI Service | 6747589 | 2017-07-14 | 2017-07-16 | 1657/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-20
132629 | DMT Tulungagung 3 | PO Released | 34439711 | A.6. TI Service | 6747589 | 2017-07-17 | 2017-07-19 | 1770/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-22
631000 | ISAT-Tlogomas | PO Released | 34439708 | A.6. TI Service | 6747589 | 2017-07-25 | 2017-07-28 | 4159/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-04-04
130576 | Dahlia - Boyolangu | PO Released | 34439706 | A.6. TI Service | 6747589 | 2017-07-14 | 2017-07-16 | 1649/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-22
130120 | JAMBANGANKEBON | PO Released | 34439705 | A.6. TI Service | 6747589 | 2017-07-17 | 2017-07-19 | 1725/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-15
132833 | IBS_Tambran | PO Released | 34439702 | A.6. TI Service | 6747589 | 2017-07-24 | 2017-07-28 | 4202/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-22
131780 | Sukowinangun | PO Released | 34439701 | A.6. TI Service | 6747589 | 2017-07-24 | 2017-07-25 | 3378/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-05-12
131779 | ISAT Magetan | PO Released | 34439699 | A.6. TI Service | 6747589 | 2017-07-24 | 2017-07-28 | 4304/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-22
130876 | XL - MAGETAN | PO Released | 34439696 | A.6. TI Service | 6747589 | 2017-07-24 | 2017-07-26 | 3545/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-22
130379 | Munginsidi - Magetan | PO Released | 34439695 | A.6. TI Service | 6747589 | 2017-07-24 | 2017-07-25 | 3321/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-22
133679 | Kutoanyar | PO Released | 34439692 | A.6. TI Service | 6747589 | 2017-07-19 | 2017-07-21 | 2276/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-06-14
131852 | DMT_KEDUNGWARU | PO Released | 34439687 | A.6. TI Service | 6747589 | 2017-07-14 | 2017-07-19 | 1759/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-23
131683 | Ngurah Rai - Tulungagung B | PO Released | 34439685 | A.6. TI Service | 6747589 | 2017-07-14 | 2017-07-16 | 1661/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-22
131684 | Ploso Kandang - Kedung Waru C | PO Released | 34439674 | A.6. TI Service | 6747589 | 2017-07-28 |  |  |  | 6747589 | 1.3. eWCC submit |  | 2017-03-22
630082 | 0 | PO Released | 34439634 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
131552 | Sultan Hasanudin - Kedungwaru D | PO Released | 34437677 | A.6. TI Service | 6747589 | 2017-07-17 | 2017-07-19 | 1751/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-23
130680 | Dusun Gempol - Sumber Gempol B | PO Released | 34437667 | A.6. TI Service | 6747589 | 2017-07-14 | 2017-07-16 | 1652/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-22
131551 | Panglima Sudirman - Tulungagung D | PO Released | 34437657 | A.6. TI Service | 6747589 | 2017-07-14 | 2017-07-16 | 1655/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-23
130512 | 0 | PO Released | 34437645 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
130067 | Candi Lontar | PO Released | 34437636 | A.6. TI Service | 6747589 | 2017-07-17 | 2017-07-25 | 3283/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-18
130020 | JUWINGANGUBENG | PO Released | 34437625 | A.6. TI Service | 6747589 | 2017-07-17 | 2017-07-19 | 1718/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-16
130021 | BUNGTOMOGUBENG | PO Released | 34437615 | A.6. TI Service | 6747589 | 2017-07-17 | 2017-07-19 | 1719/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-16
130023 | BRATANGGDWROMO | PO Released | 34437605 | A.6. TI Service | 6747589 | 2017-07-25 | 2017-07-26 | 3543/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-17
133100 | SAWOTRATAP_GF | PO Released | 34437595 | A.6. TI Service | 6747589 | 2017-07-14 | 2017-07-16 | 1682/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-18
130131 | JTSD001A-Sidoarjo Aloha | PO Released | 34437582 | A.6. TI Service | 6747589 | 2017-07-22 | 2017-07-25 | 3300/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-18
132876 | NTS_SEDAP MALAM | PO Released | 34437571 | A.6. TI Service | 6747589 | 2017-07-13 | 2017-07-19 | 1945/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-05-17
133050 | IBS_Makro Pepelegi | PO Released | 34437560 | A.6. TI Service | 6747589 | 2017-07-13 | 2017-07-19 | 1958/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-05-17
131709 | Komet Aloha | PO Released | 34437548 | A.6. TI Service | 6747589 | 2017-07-22 | 2017-07-25 | 3375/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-16
130851 | PEPELEGI | PO Released | 34437541 | A.6. TI Service | 6747589 | 2017-07-22 | 2017-07-25 | 3361/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-15
132863 | NDK_Kedungrejo | PO Released | 34437536 | A.6. TI Service | 6747589 | 2017-07-22 | 2017-07-25 | 3399/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-18
130841 | BUDURAN | PO Released | 34437532 | A.6. TI Service | 6747589 | 2017-07-22 | 2017-07-25 | 3358/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-05-10
133040 | ISAT_WAGE_PERMAI | PO Released | 34437527 | A.6. TI Service | 6747589 | 2017-07-22 | 2017-07-25 | 3406/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-05-10
130381 | Merapi - Ponorogo | PO Released | 34437522 | A.6. TI Service | 6747589 | 2017-07-17 | 2017-07-19 | 1733/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-19
130382 | Siman - Siman | PO Released | 34437515 | A.6. TI Service | 6747589 | 2017-07-24 | 2017-07-25 | 3324/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-19
130949 | XL - PATIHAN WETAN | PO Released | 34437512 | A.6. TI Service | 6747589 | 2017-07-14 | 2017-07-16 | 1653/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-19
131512 | DEMETA - PONOROGO 2 | PO Released | 34437509 | A.6. TI Service | 6747589 | 2017-07-24 | 2017-07-26 | 3556/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-20
131645 | ISAT - PONOROGO | PO Released | 34437505 | A.6. TI Service | 6747589 | 2017-07-14 | 2017-07-16 | 1659/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-19
131696 | PONOROGO | PO Released | 34437500 | A.6. TI Service | 6747589 | 2017-07-14 | 2017-07-16 | 1664/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-20
132275 | BABADAN | PO Released | 34437497 | A.6. TI Service | 6747589 | 2017-07-14 | 2017-07-16 | 1669/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-22
132352 | DMT_STO Telkom Ponorogo | PO Released | 34437494 | A.6. TI Service | 6747589 | 2017-07-27 | 2017-07-28 | 4071/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-22
132367 | DMT_Ponorogo 4 Reloc | PO Released | 34437488 | A.6. TI Service | 6747589 | 2017-07-14 | 2017-07-16 | 1671/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-19
132368 | DMT_Siman / Ponorogo 5 | PO Released | 34437481 | A.6. TI Service | 6747589 | 2017-07-17 | 2017-07-19 | 1768/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-19
132369 | IBS_Brotonegoro | PO Released | 34437477 | A.6. TI Service | 6747589 | 2017-07-14 | 2017-07-16 | 1672/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-20
132390 | DMT_Ponorogo 3 | PO Released | 34437472 | A.6. TI Service | 6747589 | 2017-07-14 | 2017-07-16 | 1674/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-19
133244 | KENITEN PONOROGO | PO Released | 34437470 | A.6. TI Service | 6747589 | 2017-07-14 | 2017-07-16 | 1683/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-19
134273 | Ponorogo | PO Released | 34437465 | A.6. TI Service | 6747589 | 2017-07-22 | 2017-07-25 | 3430/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-06-12
630086 | STP Pahitan Wetan | PO Released | 34437460 | A.6. TI Service | 6747589 | 2017-07-20 | 2017-07-25 | 3461/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-06-09
132030 | Ploso_Pacitan_GF | PO Released | 34437455 | A.6. TI Service | 6747589 | 2017-07-14 | 2017-07-16 | 1667/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-20
131910 | Sambong | PO Released | 34437450 | A.6. TI Service | 6747589 |  |  |  |  | 6747589 | 8.3. NY MSFI App |  | 2017-03-20
132695 | DMT_Kedung Kandang | PO Released | 34437442 | A.6. TI Service | 6747589 | 2017-07-22 | 2017-07-25 | 3393/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-05-12
131635 | SUMBER PORONG | PO Released | 34437436 | A.6. TI Service | 6747589 | 2017-07-14 | 2017-07-16 | 1658/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-16
134065 | CEMARA7 | PO Released | 34437431 | A.6. TI Service | 6747589 | 2017-07-20 | 2017-07-25 | 3424/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-23
131907 | SUNGKONO ML | PO Released | 34437427 | A.6. TI Service | 6747589 | 2017-07-25 | 2017-07-26 | 3572/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-05-17
132294 | SUKUN | PO Released | 34437425 | A.6. TI Service | 6747589 | 2017-07-13 | 2017-07-16 | 1670/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-22
131441 | Karang Rejo - Gempol | PO Released | 34437421 | A.6. TI Service | 6747589 | 2017-07-22 | 2017-07-25 | 3367/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-05-10
133595 | IBS_BANGIL | PO Released | 34437416 | A.6. TI Service | 6747589 | 2017-07-31 | 2017-07-31 | 4889/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-05-10
132723 | BLANDONGAN | PO Released | 34437410 | A.6. TI Service | 6747589 |  |  |  |  | 6747589 | 8.3. NY MSFI App |  | 2017-03-24
131327 | PURWOSARI | PO Released | 34437404 | A.6. TI Service | 6747589 | 2017-07-31 | 2017-08-01 | 4969/eWCC/H3I/INH/C2/VIII/2017 | 2017-08-01 | 6747589 | 1.1. eWCC approved |  | 2017-05-10
131523 | Gempol Pandaan | PO Released | 34437399 | A.6. TI Service | 6747589 |  |  |  |  | 6747589 | 8.3. NY MSFI App |  | 2017-05-10
132382 | BANGIL | PO Released | 34437393 | A.6. TI Service | 6747589 |  |  |  |  | 6747589 | 8.3. NY MSFI App |  | 2017-05-10
132306 | ISAT Bakalan Pasuruan | PO Released | 34437386 | A.6. TI Service | 6747589 |  |  |  |  | 6747589 | 8.3. NY MSFI App |  | 2017-05-10
132571 | ISAT_KRATON | PO Released | 34437383 | A.6. TI Service | 6747589 |  |  |  |  | 6747589 | 8.3. NY MSFI App |  | 2017-05-10
130590 | XL - NGERONG | PO Released | 34437377 | A.6. TI Service | 6747589 |  |  |  |  | 6747589 | 8.3. NY MSFI App |  | 2017-05-10
|  | PO Released | 34437375 |  | 6747589 |  |  |  |  | 6747589
133450 | IBS_Ploso Pacitan | PO Released | 34437369 | A.6. TI Service | 6747589 | 2017-07-17 | 2017-07-19 | 1789/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-21
132730 | BANGUNSARI | PO Released | 34437367 | A.6. TI Service | 6747589 | 2017-07-17 | 2017-07-19 | 1772/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-21
131911 | DMT_STO PACITAN | PO Released | 34437364 | A.6. TI Service | 6747589 | 2017-07-19 | 2017-07-21 | 2259/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-21
131695 | XL - ARJOWINANGUN PACITAN | PO Released | 34437355 | A.6. TI Service | 6747589 | 2017-07-17 | 2017-07-19 | 1754/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-21
130390 | Basuki Rahmad - Pacitan | PO Released | 34437348 | A.6. TI Service | 6747589 | 2017-07-24 | 2017-07-25 | 3326/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-21
132934 | STP_Gedangan Wetan | PO Released | 34437340 | A.6. TI Service | 6747589 |  |  |  |  | 6747589 | 8.3. NY MSFI App |  | 2017-03-26
130136 | JTSD002A-Sidoarjo Gedangan | PO Released | 34437333 | A.6. TI Service | 6747589 |  |  |  |  | 6747589 | 8.3. NY MSFI App |  | 2017-03-26
133927 | MANISREJO_GF | PO Released | 34437328 | A.6. TI Service | 6747589 | 2017-07-20 | 2017-07-25 | 3423/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-06-21
630225 | B2S Protelindo Oro-Oro Ombo | PO Released | 34437315 | A.6. TI Service | 6747589 | 2017-07-20 | 2017-07-25 | 3463/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-05-24
133919 | Greja Menara Advent RT | PO Released | 34437310 | A.6. TI Service | 6747589 | 2017-07-19 | 2017-07-25 | 3422/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-06-14
133917 | SUGATEN_GF | PO Released | 34437305 | A.6. TI Service | 6747589 | 2017-07-22 | 2017-07-25 | 3420/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-18
131905 | KARANGDUREN | PO Released | 34437301 | A.6. TI Service | 6747589 | 2017-07-22 | 2017-07-25 | 3380/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-05-02
131751 | XL Parang Argo | PO Released | 34437297 | A.6. TI Service | 6747589 | 2017-07-17 | 2017-07-19 | 1758/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-19
130999 | XL - SIDORAHAYU | PO Released | 34437284 | A.6. TI Service | 6747589 | 2017-07-17 | 2017-07-19 | 1744/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-27
133290 | XL_Arjosari | PO Released | 34437270 | A.6. TI Service | 6747589 | 2017-07-18 | 2017-07-19 | 1788/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-17
134292 | RST. Soepraoen Malang | PO Released | 34437256 | A.6. TI Service | 6747589 | 2017-07-22 | 2017-07-25 | 3431/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-05-12
131602 | KEBON AGUNG | PO Released | 34437241 | A.6. TI Service | 6747589 | 2017-07-26 | 2017-07-28 | 4300/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-16
130307 | Bakalankrajan | PO Released | 34437231 | A.6. TI Service | 6747589 | 2017-07-31 |  |  |  | 6747589 | 1.3. eWCC submit |  | 2017-03-15
130759 | XL - BULULAWANG | PO Released | 34437221 | A.6. TI Service | 6747589 | 2017-07-22 | 2017-07-25 | 3350/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-05-12
132276 | LAHAN IBU SUNARTI | PO Released | 34437208 | A.6. TI Service | 6747589 | 2017-07-24 | 2017-07-25 | 3384/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-05-02
130619 | KH. Malik Dalam - Kedung Kandang | PO Released | 34437195 | A.6. TI Service | 6747589 | 2017-07-31 | 2017-08-01 | 4971/eWCC/H3I/INH/C2/VIII/2017 | 2017-08-01 | 6747589 | 1.1. eWCC approved |  | 2017-05-12
132836 | Axis_Dirgantara Auri | PO Released | 34437181 | A.6. TI Service | 6747589 | 2017-07-22 | 2017-07-25 | 3396/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-05-12
130280 | Kol.Sugiono | PO Released | 34437159 | A.6. TI Service | 6747589 | 2017-07-18 | 2017-07-19 | 1732/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-15
130399 | Gatot Subroto - Turen | PO Released | 34437146 | A.6. TI Service | 6747589 | 2017-07-24 | 2017-07-25 | 3328/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-15
132556 | IBS_Kepanjen | PO Released | 34437133 | A.6. TI Service | 6747589 | 2017-07-24 | 2017-07-28 | 4257/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-15
132757 | KEDUNG PEDARINGAN | PO Released | 34437094 | A.6. TI Service | 6747589 | 2017-07-17 | 2017-07-19 | 1773/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-17
212231 | MALINO, SULAWESI | PO Released | 34436729 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212256 | Biringbulu | PO Released | 34436726 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212254 | Taman roya | PO Released | 34436725 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212268 | Palekko | PO Released | 34436723 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212266 | Bulukunyi-Polsel-Takalar | PO Released | 34436719 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212271 | Padi Valley | PO Released | 34436717 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212358 | Bili Bili | PO Released | 34436711 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212363 | Parigi | PO Released | 34436705 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212465 | Repeater Bili Bili | PO Released | 34436702 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212135 | Lekopancing | PO Released | 34436698 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212146 | Benteng Gajah | PO Released | 34436696 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212407 | SUMANGKI | PO Released | 34436693 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212127 | Moncong Bulu | PO Released | 34436690 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212111 | Pakato | PO Released | 34436688 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212764 | Jembatan Tol | PO Released | 34436686 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212129 | Bili Bili | PO Released | 34436683 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212113 | Bulu Jaya | PO Released | 34436682 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212102 | Bonto Kadato | PO Released | 34436679 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212089 | Malewang | PO Released | 34436678 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212131 | Tanralili | PO Released | 34436677 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212572 | PTPN | PO Released | 34436673 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212122 | Pattalassang | PO Released | 34436670 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212108 | Panyangkalang | PO Released | 34436665 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212055 | Limbung | PO Released | 34436663 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212023 | Kalabirang | PO Released | 34436662 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212003 | Bontonompo | PO Released | 34436660 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212001 | GALESONG,SULSEL | PO Released | 34436656 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
213296 | Citra Sudiang | PO Released | 34436652 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
213293 | Pacccerakang – MESS AURI | PO Released | 34436650 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
213302 | Taroada-Maros | PO Released | 34436647 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212072 | TAKALAR,SUL-SEL | PO Released | 34436641 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212054 | Mangara Bombang | PO Released | 34436639 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
213303 | Sudiang - BPS Dalam | PO Released | 34436633 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
|  | PO Released | 34432349 |  | 30784695 |  |  |  |  | 30784695
213304 | Paccerakang - Telkom X | PO Released | 34436598 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
|  | PO Released | 34398394 |  | 6540750 |  |  |  |  | 6540750
130151_130152 | - | PO Released | 34398391 | A.6. TI Service ALU | 13124250 |  |  |  |  | 13124250
131013_130187 | - | PO Released | 34398385 | A.6. TI Service ALU | 10046250 |  |  |  |  | 10046250
130155_new130155 | - | PO Released | 34398383 | A.6. TI Service ALU | 10046250 |  |  |  |  | 10046250
130145_130146 | - | PO Released | 34398380 | A.6. TI Service ALU | 6540750 |  |  |  |  | 6540750
132568_137003 | - | PO Released | 34398378 | A.6. TI Service ALU | 6540750 |  |  |  |  | 6540750
130542_130585 | - | PO Released | 34398376 | A.6. TI Service ALU | 6540750 |  |  |  |  | 6540750
130681_130181 | - | PO Released | 34398375 | A.6. TI Service ALU | 6540750 |  |  |  |  | 6540750
132275_130384 | - | PO Released | 34398374 | A.6. TI Service ALU | 6540750 |  |  |  |  | 6540750
132189_131013 | - | PO Released | 34398373 | A.6. TI Service ALU | 6540750 |  |  |  |  | 6540750
132257_130387 | - | PO Released | 34398371 | A.6. TI Service ALU | 6540750 |  |  |  |  | 6540750
135144_131734 | - | PO Released | 34398370 | A.6. TI Service ALU | 6540750 |  |  |  |  | 6540750
130155_new130155 | - | PO Released | 34366098 | Survey ALU | 2474464 |  |  |  |  | 2474464 | 5.1 Waiting Doc TSSR |  | 2017-05-03
131013_130187 | - | PO Released | 34366097 | Survey ALU | 2474464 |  |  |  |  | 2474464 | 5.1 Waiting Doc TSSR |  | 2017-04-15
130145_130146 | - | PO Released | 34366095 | Survey ALU | 2474464 |  |  |  |  | 2474464 | 5.1 Waiting Doc TSSR |  | 2017-04-15
132568_137003 | - | PO Released | 34366091 | Survey ALU | 2474464 |  |  |  |  | 2474464 | 5.1 Waiting Doc TSSR |  | 2017-04-27
130542_130585 | - | PO Released | 34366088 | Survey ALU | 2474464 | 2017-07-31 |  |  |  | 2474464 | 1.3. eWCC submit |  | 2017-04-10
130681_130181 | - | PO Released | 34366083 | Survey ALU | 2474464 |  |  |  |  | 2474464 | 5.1 Waiting Doc TSSR |  | 2017-04-11
132275_130384 | - | PO Released | 34366080 | Survey ALU | 2474464 |  |  |  |  | 2474464 | 5.1 Waiting Doc TSSR |  | 2017-04-13
132022_131998 | - | PO Released | 34366078 | Survey ALU | 2474464 |  |  |  |  | 2474464 | 5.1 Waiting Doc TSSR |  | 2017-04-11
132189_131013 | - | PO Released | 34366075 | Survey ALU | 2474464 |  |  |  |  | 2474464 | 5.1 Waiting Doc TSSR |  | 2017-04-15
132257_130387 | - | PO Released | 34366070 | Survey ALU | 2474464 |  |  |  |  | 2474464 | 5.1 Waiting Doc TSSR |  | 2017-04-12
135144_131734 | - | PO Released | 34366017 | Survey ALU | 2474464 |  |  |  |  | 2474464 | 5.1 Waiting Doc TSSR |  | 2017-04-12
212110 | Moncong Maros | PO Released | 34332701 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
212909 | Terminal Maros 2 | PO Released | 34332690 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
212780 | STO Kima | PO Released | 34332681 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
212007 | Pakkaba Galesong | PO Released | 34332673 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
212709 | Pallantikang Pangkasalo | PO Released | 34332667 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
212720 | Talamangape-Allepolea | PO Released | 34332663 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
212714 | Bonto Kio | PO Released | 34332655 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
215028 | Bandara Hasanudin | PO Released | 34332649 | A.6. TI Service | 9318110 | 2017-07-28 |  |  |  | 9318110 | 1.3. eWCC submit |  | 2017-04-15
212002 | Bonto Lebang - Galesong Utara | PO Released | 34332633 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
|  | PO Released | 34332621 |  | 9318110 |  |  |  |  | 9318110
212781 | Mambue | PO Released | 34332617 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212786 | Baddoka | PO Released | 34332611 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
213114 | Paccerakkang-Daya | PO Released | 34332607 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
212633 | Pasar Daya | PO Released | 34332600 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
|  | PO Released | 34332578 |  | 9318110 |  |  |  |  | 9318110
212121 | Bumi Taniaga Permai | PO Released | 34332563 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
212710 | Batangase | PO Released | 34332544 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
213133 | Taman Sudiang | PO Released | 34332527 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
213115 | Sudiang-BPS | PO Released | 34332519 | A.6. TI Service | 9318110 | 2017-07-27 |  |  |  | 9318110 | 1.3. eWCC submit |  | 2017-04-15
213122 | Mandai | PO Released | 34332509 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
212896 | Maccopa | PO Released | 34332498 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
212109 | KIMA 8 | PO Released | 34332491 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212789 | PAI | PO Released | 34332485 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212929 | Allepolea - Lau | PO Released | 34332480 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
|  | PO Released | 34332471 |  | 9318110 |  |  |  |  | 9318110
212639 | BENTENGE BUTATTOA UTARA-PETTUADAE-TURIKALE | PO Released | 34332462 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
213095 | 3G_Dishub Daya | PO Released | 34332454 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
212791 | STO Sudiang | PO Released | 34332443 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
212793 | Paccerakkang Daya | PO Released | 34332436 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
212711 | Palantikang | PO Released | 34332424 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
212717 | Kantor Bupati Maros | PO Released | 34332418 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
212107 | Kima 2 | PO Released | 34332411 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
212726 | Barombong | PO Released | 34332404 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
213149 | Aliri Tenggae - Pasar Maros | PO Released | 34332386 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
213253 | Paccerakang – Ruko Pelangi | PO Released | 34332368 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
213097 | Sanrangan | PO Released | 34332350 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
213098 | Daeng Ramang | PO Released | 34332332 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
212785 | Mongcongloe Lappara | PO Released | 34332318 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
213116 | 3G_Daya Kima | PO Released | 34332307 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
213224 | Sudiang Raya - Batara Ugi | PO Released | 34332298 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
213143 | TBG Citra | PO Released | 34332290 | A.6. TI Service | 9318110 |  |  |  |  | 9318110
212114 | Sudiang Asrama Haji | PO Released | 34332282 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
212790 | RS Kusta Daya | PO Released | 34332267 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
212879 | Maros Kota | PO Released | 34332252 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
213131 | ATKP Maros | PO Released | 34332235 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
213223 | Paccerakkang - RS. Dr. Tadjuddin Chalid | PO Released | 34332164 | A.6. TI Service | 9318110 |  |  |  |  | 9318110 | 2.2. NY create in eWCC
130175 | Basuki Rahmad Tuban | PO Released | 34319803 | A.6. TI Service | 6747589 | 2017-07-24 | 2017-07-24 | 2634/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-22
630506 | XLPandaan | PO Released | 34315125 | A.6. TI Service | 6747589 |  |  |  |  | 6747589 | 8.3. NY MSFI App |  | 2017-03-24
|  | PO Released | 34314733 |  | 6747589 |  |  |  |  | 6747589
|  | PO Released | 34314681 |  | 6747589 |  |  |  |  | 6747589
131735 | Ngronggo Kota | PO Released | 34239369 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
130142 | Mayjen Panjaitan-Taman | PO Released | 34239239 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
133174 | IBS_Babat | PO Released | 34238876 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
132776 | DCS_PANYURAN | PO Released | 34238864 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
133173 | DMT_BABAT PLAOSAN | PO Released | 34238851 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
133631 | DMT_STO Babat | PO Released | 34238838 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
133172 | Widang-Babat | PO Released | 34238826 | A.6. TI Service | 6747589 |  |  |  |  | 6747589 | 8.3. NY MSFI App |  | 2017-03-26
131938 | Karangrejo Palang_GF | PO Released | 34238812 | A.6. TI Service | 6747589 |  |  |  |  | 6747589 | 8.3. NY MSFI App |  | 2017-03-22
131803 | ISAT Tuban Timur | PO Released | 34238800 | A.6. TI Service | 6747589 |  |  |  |  | 6747589 | 8.3. NY MSFI App |  | 2017-03-22
132385 | DMT_Tuban 3 | PO Released | 34238786 | A.6. TI Service | 6747589 | 2017-07-11 | 2017-07-14 | 1608/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-24
131422 | Al - Falah - Tuban | PO Released | 34238773 | A.6. TI Service | 6747589 |  |  |  |  | 6747589 | 8.3. NY MSFI App |  | 2017-03-23
130583 | NURAMA-TUBAN | PO Released | 34238761 | A.6. TI Service | 6747589 | 2017-07-28 |  |  |  | 6747589 | 1.3. eWCC submit |  | 2017-03-22
132717 | DMT_STO TUBAN | PO Released | 34238749 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
131919 | Paciran_GF | PO Released | 34238734 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
132706 | Perum Semen Gresik T | PO Released | 34238715 | A.6. TI Service | 6747589 | 2017-08-01 |  |  |  | 6747589 | 1.3. eWCC submit |  | 2017-03-24
132355 | DMT_Tuban Relok | PO Released | 34238690 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
132302 | XL_Karangagung_Tuban | PO Released | 34238670 | A.6. TI Service | 6747589 |  |  |  |  | 6747589 | 8.3. NY MSFI App |  | 2017-03-22
130584 | Pahlawan - Semanding | PO Released | 34238647 | A.6. TI Service | 6747589 | 2017-07-13 | 2017-07-16 | 1650/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-22
132712 | IBS_Ronggo Mulyo | PO Released | 34238622 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
131711 | PALANG | PO Released | 34238602 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
133619 | STI Tuban | PO Released | 34238578 | A.6. TI Service | 6747589 | 2017-07-19 | 2017-07-25 | 3412/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-24
131939 | Leran_Kulon_GF | PO Released | 34238558 | A.6. TI Service | 6747589 | 2017-07-12 | 2017-07-16 | 1666/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-22
131716 | XL Paciran | PO Released | 34238530 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
131918 | Brondong_GF | PO Released | 34238496 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
131937 | SugihWaras_GF | PO Released | 34238468 | A.6. TI Service | 6747589 | 2017-07-26 |  |  |  | 6747589 | 1.3. eWCC submit |  | 2017-03-22
132555 | Axis_Ngasem | PO Released | 34238295 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
131676 | PARE | PO Released | 34238275 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
132372 | XL_Winongo Madiun | PO Released | 34238252 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
132375 | DMT_Ds.Kranggan (Simpang) | PO Released | 34238229 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
133403 | XL_Mojoroto | PO Released | 34238143 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
131679 | TSEL INKA DCS 1 | PO Released | 34238109 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
131429 | KH. Dewantoro - Badas | PO Released | 34238051 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
132691 | XL_LANGENHARJO KEDIRI 2 | PO Released | 34237990 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
130767 | XL - SEMEN KEDIRIi | PO Released | 34237963 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
132377 | XL_Universitas Kediri | PO Released | 34237910 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
131728 | PELEM_KDR | PO Released | 34237864 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
132533 | Nglames_GF | PO Released | 34237850 | A.6. TI Service | 6747589 | 2017-07-22 | 2017-07-25 | 3389/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-18
131430 | Gede - Pare | PO Released | 34237739 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
130977 | XL - GUDANG GARAM KEDIRI | PO Released | 34237656 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
132560 | NAMBAAN | PO Released | 34237625 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
133715 | Stadion Brawijaya Kediri | PO Released | 34237597 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
130522 | Inspeksi Pengairan - Mojoroto | PO Released | 34237548 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
131624 | KARTOHARJO | PO Released | 34237518 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
131846 | SEMEN_KDR | PO Released | 34237433 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
130839 | NGLAMES | PO Released | 34237403 | A.6. TI Service | 6747589 | 2017-07-26 | 2017-07-28 | 4326/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-18
133356 | XL_Pesantren Kediri | PO Released | 34237387 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
132552 | ISAT_DOKO GAMPENGREJO | PO Released | 34237370 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
130849 | JIWAN | PO Released | 34237324 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
131365 | Srikaton - Kartoharjo | PO Released | 34237306 | A.6. TI Service | 6747589 | 2017-07-12 | 2017-07-16 | 1654/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-18
131686 | Pilang Mulya - Kartoharjo | PO Released | 34237297 | A.6. TI Service | 6747589 | 2017-07-12 | 2017-07-16 | 1663/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-18
132554 | ISAT_Ngadismo_kediri | PO Released | 34237271 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
631083 | KEDIRI1 | PO Released | 34237261 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
131736 | Katang | PO Released | 34237252 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
132574 | MANISRENGGO KOTA KEDIRI | PO Released | 34237241 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
130884 | XL - PANDEAN MADIUN | PO Released | 34237231 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
130152 | Asrama TNI KODIM 0809 | PO Released | 34237222 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
131564 | ISAT - DUNGUS MADIUN | PO Released | 34237201 | A.6. TI Service | 6747589 | 2017-07-12 | 2017-07-16 | 1656/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-20
631019 | Kandya'an | PO Released | 34237182 | A.6. TI Service | 6747589 | 2017-07-20 | 2017-07-25 | 3472/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-05-17
130145 | Tawang Sari - Kartoharjo | PO Released | 34237164 | A.6. TI Service | 6747589 | 2017-07-12 | 2017-07-16 | 1645/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-18
130240 | Raya Jatikerto-Kromengan | PO Released | 34237144 | A.6. TI Service | 6747589 | 2017-07-12 | 2017-07-16 | 1647/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-13
131855 | JIWAN | PO Released | 34237123 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
130485 | Indrokiloselatan-Lawang | PO Released | 34237105 | A.6. TI Service | 6747589 | 2017-07-20 | 2017-07-21 | 2228/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-16
132559 | PAMENANG | PO Released | 34237087 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
131844 | PROLIMAN | PO Released | 34237064 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
131688 | Mliwis - Mangunharjo | PO Released | 34237046 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
131697 | MADIUN_CITY | PO Released | 34237027 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
130645 | XL - GEDANG SEWU | PO Released | 34237004 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
130154 | Kantor Pos Kediri-Mrican | PO Released | 34236974 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
130881 | XL - MANISREJO | PO Released | 34236933 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
130481 | Klotok - Mojoroto | PO Released | 34236900 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
631026 | Isat_BandarLor | PO Released | 34236859 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
134090 | ISAT_KEDIRI | PO Released | 34236845 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
133740 | Protelindo LANAL Malang | PO Released | 34236827 | A.6. TI Service | 6747589 | 2017-07-19 | 2017-07-25 | 3415/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-06-21
132297 | XL_Tiron_Madiun | PO Released | 34236803 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
131510 | NURAMA - YOS SUDARSO | PO Released | 34236788 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
130148 | Sunan Bonang - Kartoharjo | PO Released | 34236776 | A.6. TI Service | 6747589 | 2017-07-12 | 2017-07-16 | 1646/eWCC/H3I/INH/C1/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-18
131687 | Joyodanu - Taman C | PO Released | 34236765 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
130302 | Raya Mulyorejo-Sukun | PO Released | 34236688 | A.6. TI Service | 6747589 | 2017-07-11 | 2017-07-13 | 1564/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 6747589 | 1.1. eWCC approved |  | 2017-03-13
134285 | B2S_Protelindo_Banjar Kidul | PO Released | 34235316 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
131546 | KH.Wahid Hasyim - Mojoroto | PO Released | 34235223 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
|  | PO Released | 34235195 |  | 6747589 |  |  |  |  | 6747589
133401 | IBS_Kediri Town | PO Released | 34235188 | A.6. TI Service | 6747589 |  |  |  |  | 6747589
62104 | SARANG_ELANG | PO Released | 34455523 | A.6. TI Service SouthSum | 8779878 |  |  |  |  | 8779878 | 8.3. NY MSFI App |  | 2017-03-26
60587 | Imam Bonjol - Sukaraja | PO Released | 34454891 | A.6. TI Service SouthSum | 7247174 |  |  |  |  | 7247174 | 4.7. Waiting Doc MSFI |  | 2017-04-03
631052 | XL Jongbiru | PO Released | 34203559 | A.6. TI Service | 2269816 | 2017-07-22 | 2017-07-25 | 3476/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 2269816 | 1.1. eWCC approved |  | 2017-03-21
631057 | STTOPARE | PO Released | 34203564 | A.6. TI Service | 2269816 | 2017-07-25 | 2017-07-28 | 4171/eWCC/H3I/INH/C2/VII/2017 | 2017-07-01 | 2269816 | 1.1. eWCC approved |  | 2017-03-24
133921 | KARTOHARJO_GF | PO Released | 34437325 | A.6. TI Service | 6747589 |  |  |  |  | 6747589 | 8.3. NY MSFI App |  | 2017-03-26
60644 |  | PO Released | 34899802 |  | 6281692 |  |  |  |  | 6281692 | 2.2. NY create in eWCC
62139 |  | PO Released | 34899796 |  | 6281692 |  |  |  |  | 6281692 | 2.2. NY create in eWCC
60141 |  | PO Released | 34899784 |  | 6281692 |  |  |  |  | 6281692 | 2.2. NY create in eWCC
60774 |  | PO Released | 34899777 |  | 6281692 |  |  |  |  | 6281692 | 2.2. NY create in eWCC
60772 |  | PO Released | 34899774 |  | 6281692 |  |  |  |  | 6281692
62185 |  | PO Released | 34899770 |  | 6281692 |  |  |  |  | 6281692 | 2.2. NY create in eWCC
62193 |  | PO Released | 34899763 |  | 6281692 |  |  |  |  | 6281692 | 2.2. NY create in eWCC
60776 |  | PO Released | 34899752 |  | 6281692 |  |  |  |  | 6281692 | 2.2. NY create in eWCC
62561 |  | PO Released | 34899747 |  | 6281692 |  |  |  |  | 6281692 | 2.2. NY create in eWCC
60762 |  | PO Released | 34899745 |  | 6281692 |  |  |  |  | 6281692
62119 |  | PO Released | 34899721 |  | 6281692 |  |  |  |  | 6281692 | 2.2. NY create in eWCC
61733 |  | PO Released | 34899718 |  | 6281692 |  |  |  |  | 6281692 | 2.2. NY create in eWCC
62060 |  | PO Released | 34899565 |  | 6281692 |  |  |  |  | 6281692 | 2.2. NY create in eWCC
62130 |  | PO Released | 34899539 |  | 6281692 |  |  |  |  | 6281692
631044 | IBS BANK SINARMAS | PO NY Release |  |  | 6747589 |  |  |  |  | 6747589 | 3.3. PO NY ready
133307 | Protelindo_Wisma Sier ex B2S Protelindo Kalibokor | PO NY Release |  |  | 2186369 |  |  |  |  | 2186369 | 3.3. PO NY ready
60142 |  | PO NY Release |  |  | 6281690 |  |  |  |  | 6281690 | 3.3. PO NY ready
60744 | Nilam Bacang | PO Released | 34899777 | A.6. TI Service SouthSum | 6281690 |  |  |  |  | 6281690 | 2.2. NY create in eWCC
130066 | Pucang Anom-Sidoarjo | PO NY Release |  |  | 6747589 |  |  |  |  | 6747589 | 3.3. PO NY ready

## Sheet2
Issue | Detail Remark
1.0. Carry Over
1.1. eWCC approved
1.2. WCC manual approved
1.3. eWCC submit
1.4. WCC manual submit
1.5. eWCC Rejected
eWCC | 2.1. MS date NA
2.2. NY create in eWCC
2.3. Scope Detail in eWCC NA
2.4. Supporting Doc in eWCC NA
2.5. eWCC Recall
2.6. No "Submit"
2.7. WCC Detail Preparation "no record found"
2.8. Different Term of Payment
2.9. Wrong SOW between PO and eWCC
2.10. Wrong Ewcc Status
PO & IPM | 3.1. PO NY create in IPM
3.3. PO NY ready
3.2. Need Check PO softcopy
3.4. Need Revise PO
3.5. Check Site ID in HC PO
3.6. Check Site ID in HC PO, revisi IPM
3.7. Check Site ID in HC PO, revisi eWCC
Document | 4.1. Waiting Doc HS
4.2. Waiting Doc SA
4.3. Waiting Doc ATF
4.4. Waiting Doc PCC
4.5. Waiting Doc Punchlist
4.6. Waiting Doc PMR
4.7. Waiting Doc MSFI
4.8. Waiting Doc DN
4.9. Waiting CAF
5.0 Waiting MOM LD
5.1 Waiting Doc TSSR
Implementation | 8.1. NY ATP
8.2. PL Open
8.3. NY MSFI App
9.1. Cancel PO
9.2. Cancel WCC
10. Implemented by Other Partner